## Front
Felix Hoare - 1908089
Elemental cost plan of Y Fforwm Building.
03-05-2022

## Information Used
Information Used & Assumptions
1 | Information Used
Stride Treglown Drawings;
Proposed Ground Floor Plan
Proposed First Floor Plan
Proposed Second Floor Plan
Curtain Wall Elevations Sheet 1
Curtain Wall Elevations Sheet 2
Technical Elevations Sheet 1
Technical Elevations Sheet 2
Library - Door Schedule
Library - Door Elevations
Window Elevations
2 | General assumptions;
Due to insufficient design information, I have assumed that the roof is constructed using trusses at 600mm centres.
I have assumed that the aluminium sheet roof is applied to ply sheathing substraight.
Due to the Corona Virus pandemic and the increased cost of materials, we have assumed all costs taken from spoons are of the highest rate.
I have assumed a meterage of 250m for the connection of external services due to insufficient information on the drawings, I have deemed this the most appropriate rate given the distance from the existing mains supply.
I have assumed the street lighting will be based on the same specification as an estate road area on an assumption that there will be 50 columns.
As there is no specification, I have assumed that the wall finishes are a standard one miss coat and two coats of emulsion to both the internal and external skins.
I have not provided a cost for ceiling finishes due to the ceiling in the library block having a concrete board finish.
I have assumed that the carpet as ' Carpet tiles; including underlay, edge grippers heavy domestic duty' is the same throughout the whole building.
I have assumed that the vinyl flooring is the same throughout the whole building.
I have based the cost of the solar panels on the residential cost as this is the only cost that is available through using Spons.
Column meterage rate has been calculated at 8.2lm x 36
1 | Pile Caps size are assumed at 900 mm × 900 mm × 1000 mm; 1–2 piles
2 | Rate of the supply and install of concrete piles has been based on 600mm dia reinforced concrete CFA piles as there is no rate for 500mm.
The roof has been priced based on a timber trussed roof design. Despite the actual design being a cut roof, there was not an accurate rate in Spons based on this design.
An allowance has been made for trims and flashings of 5 percent of the overall cost of the roof.
3 | General notes and exclusions;
All included costs are subject to variation following design development.
Risks associated with BREXIT are not considered.
A risk allowance of 10% is included for this estimate.
VAT is excluded from the estimate.
Works will be undertaken in a single phase.

## Summary Original
Project details |  | NRM1 elemental cost plan UWTSD Library
Description |  | Y Fforwm Building
Works cost estimate
Cost
Building works estimate
| Group element 0 | FACILITATING WORKS - N/A | 0
| Group element 1 | SUBSTRUCTURE | 324945.88
| Group element 2 | SUPERSTRUCTURE | 1606186.0396
| Group element 3 | INTERNAL FINISHES | 262266.883
| Group element 4 | FITTINGS AND FURNISHINGS | 0
| Group element 5 | SERVICES | 2292504.75 | 0
| Group element 8 | EXTERNAL WORKS - N/A | 287250
| Group element 9 | MAIN CONTRACTOR'S PRELIMINARIES | 447435.7673
Works cost estimate (sub total A) |  |  | 5220589.3199
Project design team fees and other development costs (sub total B)
Base cost estimate A + B (sub total C) |  |  | 5220589.3199
| Group element 13 | Risk allowance @
Total Risk allowances (sub total D) |  |  | 0
0
Total Construction Cost (C + D) |  |  | 5220589.3199
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## NRM1 Breakdown
Cost Plan for Y Fforwm Building
NRM 1 phaseologies
Elemental Cost Plan
Elements in red are NRM1 Phraseologies
Ref. | Element | Quantity / unit |  |  | Rate | Sub-Total | Group-Total | Notes
[5 empty] | £ | £ | £
0 | FACILITATING WORKS - N/A | [5 empty] | 0
0.1 | Toxic/hazardous material
| Toxic or hazardous material removal: Details to be stated e.g Removal of asbestos |  |  | item | 0 | 0
Contaminated land
| Contaminated ground material removal: Details to be stated. |  |  | item | 0 | 0
0.2 | Major demolition works
Demolition of entire buildings: details to be stated.
| Demolition of entire structure |  |  | item | 0 | 0
1 | SUBSTRUCTURE | [5 empty] | 324945.88
1.1 | Foundations
| Excavtion and installation of pile mat |  | 372.4 | m3 | 13.7 | 5101.88 |  | Rate Includes: Enabling works excavate to form piling mat; supply and lay imported hardcore – recycled brick and similar to form piling mat
| Mobilisation and Removal of Piling Plant |  | 1 | Item | 23000 | 23000 |  | Rate Includes:provision of plant (1 nr rig); including bringing to and removing from site; maintenance, erection and dismantling at each pile position
| Supply and install of Piling |  | 624 | m | 100 | 62400 |  | Rate Includes : Supply and install concrete Continuous Flight Auger (CFA) piles; cart away inactive spoil; measure total length of pile
| Pile Caps |  | 96 | nr | 910 | 87360 |  | Rate Includes: Excavate pit in firm ground by machine, partial backfill, partial disposal, support, compaction, cut off pile and prepare reinforcement, formwork; reinforced in situ concrete cap 25 N/mm²; reinforcement at 50 kg/m³
| Ground floor slab |  | 952 | m2 | 125 | 119000 |  | Rate includes: Mechanical excavation to reduce levels, disposal, level and compact, hardcore bed blinded with sand, 1200 gauge polythene damp-proof membrane, in situ concrete 20.00 N/mm² – 20 mm aggregate (1:2:4)
| Slab Insulation |  | 952 | m2 | 29.5 | 28084 |  | Rate Includes :Kingspan Thermafloor TF70 (Thermal conductivity 0.022 W/mK) rigid urethane floor insulation for solid concrete and suspended ground floors
2 | SUPERSTRUCTURE | [5 empty] | 1606186.0396
2.1 | Frame
Structural steel frame, including fittings and fixings: details to be stated.
| Steel frame;composite beam and slab floors |  | 295.2 | m2 | 235 | 69372 |  | Rate Includes: einforced in situ concrete columns, bar reinforcement, formwork. Generally all formwork assumes four uses reinforcement rate 180 kg/m³; column size 300mm x 600mm.
2.2 | Upper Floors
| Concrete upper floors |  | 1729.38 | m2 | 135 | 233466.3 |  | Rate Includes: Post-tensioned concrete upper floors reinforced post-tensioned suspended concrete slab 150–225 mm thick, 40 N/ mm2 reinforcement 60 kg/m3, formwork
2.3 | Roof
Roof structure - pitched roofs: details, including design loads (kN/M2), spans (m) and angle of pitch (degtrees). To be stated
| Aluminium Roofing |  | 1320.8 | m2 | 80 | 105664 |  | Rate Includes: Kalzip standard natural aluminium; 0.9 mm thick; 180 mm glassfibre insulation; vapour control layer; liner sheets; (U-value = 0.25 W/m2K)
| Construction of pitched roof to second floor |  | 1320.8 | m2 | 43 | 56794.4 |  | Rate Includes: Softwood trussed pitched roofs; structure only Timber roof trusses and bracings only; plan area comprising 75 mm × 50 mm roof trusses at 600 mm centres
| Down pipes |  | 44.4 | m | 95 | 4218 |  | Rate Includes: Aluminum downpipes based on a Primary school extention
| Gutters |  | 104 | m | 85 | 8840 |  | Rate Includes: Aluminum gutters based on a Primary school extention
| Rooflights |  | 45.06 | m2 | 870 | 39202.2 |  | Rate Includes: Rooflights/Patent Glazing and Glazed Roofs Rooflights individual polycarbonate rooflights; rectangular; manual opening
| Allowance for trims and flashings |  | 1 | item | 10735.93 | 10735.93 |  | Rate is an assumption based on 5 percent of the overall cost of the Roof.
2.4 | Stairs & Ramps
Stair structures: details, includng vrtical rise of starcase to be stated
| Main Staircase |  | 4 | no | 5431.43 | 21725.72 |  | Rate Includes: precast concrete staircase 1800 mm wide; one full width half landing;3750 mm rise
| Balustrading to first floor terrace and stairwell |  | 43 | m | 1075 | 46225 |  | Rate Includes: Balustrading and handrails stainless steel and structural glass balustrade
2.5 | External Walls
External walls: Details to be stated.
| Cladding to elevations |  | 394.72 | m2 | 65.83 | 25984.4176 |  | Rate Includes:Facing bricks; machine-made facings; in gauged mortar (1:1:6) Stretcher bound
| Aluminimum cladding to external elevations |  | 273.82 | m2 | 305 | 83515.1 |  | Rate includes :Trespa single skin rainscreen cladding, 8 mm thick panel, with secondary support/frame system; adhesive fixed panels;
| Extra over for projected fins to elevation windows 8.6m x 6m |  | 288.6 | nr | 170.82 | 49298.652 |  | Rate Includes: Louvres, Brise Soleils and frames; polyester powder coated aluminium; fixing in position including brackets.
2.6 | Windows and external doors
Windows : details, including overall size of opening (mm) to be stated.
Windows
| Type 1 2400 x 460 mm |  | 4.416 | m2 | 625 | 2760
| Type 2 2400 x 1360 mm |  | 45.696 | m2 | 625 | 28560 |  | Rate Includes: Aluminium windows; Powder coated; 40% of faade area
| Type 2a 2400 x 1360 mm |  | 16.32 | m2 | 625 | 10200
| Type 3 2400 x 1360 mm |  | 9.792 | m2 | 625 | 6120
| Type 3a 2400 x 1360 mm |  | 3.264 | m2 | 625 | 2040
| Type 4 2400 x 1360 mm |  | 3.264 | m2 | 625 | 2040
| Type 5 3225 x 1360 mm |  | 30.702 | m2 | 625 | 19188.75
| Type 6 3225 x 1360 mm |  | 13.158 | m2 | 625 | 8223.75
| Type 7 3450 x 3265 mm | [6 empty] | This rate has been included in section 2.3
External doors: details, including type, number of door leaves (nr) size of each door leaf (mm) and overall size of opening (mm) to be stated.
External doors
| Curtain wall system incorporating single leaf door |  | 719 | m2 | 914.6 | 657597.4 |  | Rate Includes: Curtain walling with powder coated aluminium frame. 2 Revolving Doors ; 3 or 4 wing 3000 mm dia.,2200 mm internal heigh.
| Steel door to plant/Bin access, twin leaf |  | 2 | no | 1134.18 | 2268.36 |  | Rate Includes: Pair of gates and gate posts to match steel fencing with flat section framing and braces.
| BOH entrance door, 1.5 leaf, aluminium |  | 0 | no | 0 | 0
2.7 | Internal walls
Internal walls:details, including thickness, to be stated
| 140mm block wall |  | 430.47 | m2 | 46 | 19801.62 |  | Rate Includes: Partitions; 140mm blockwork
| Cublicles Walls |  | 85.59 | m2 | 40 | 3423.6 |  | Rate Includes: Block partitions aerated/lightweight block partitions 100 mm thick
| extra for plaster and emulsion |  | 684.36 | m2 | 10 | 6843.6 |  | Rate Includes: Plaster skim with emulsion paint finish to internal and external skin
fixed partitions:details, including thickness, to be stated
| New internal metal stud partitions, including skim to receive plaster both sides |  | 1180.665 | m2 | 56 | 66117.24 |  | Rate Includes: Metal stud and board partitions; height range from 2.40 m to 3.30 m 73 mm partition; 48 mm studs and channels; one layer of 12.5 mm Gyproc Wallboard each side; joints filled with joint filler and joint tape;
2.8 | Internal doors & screens
Internal doors: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated.
| single leaf internal door |  | 38 | nr | 420 | 15960 |  | Rate Includes: Standard doors; cellular core; softwood; softwood architrave; aluminium ironmongery (latch only) single leaf; Sapele veneered finish
Fire resisting doors: details, including type, number of door leaves (nr), fire rating (hours), size of each door leaf (mm), and overall size of opening (mm), to be stated.
| Fire rated doors single leaf, timber veneer with vision panel |  |  | nr | 0 | 0
| FD30s Single |  | 15 | nr | 610 | 9150 |  | Rate Includes:Standard fire doors; cellular core; softwood lining; softwood architrave; aluminuim ironmongery (lockable, self-closure); painting or polishing; single leaf; Oak veneered; 30 min fire resistance; polished
| FD60s Single |  | 5 | nr | 950 | 4750 |  | Rate Includes:Standard fire doors; cellular core; softwood lining; softwood architrave; aluminuim ironmongery (lockable, self-closure); painting or polishing; single leaf; Oak veneered; 60 min fire resistance; polished
| FD60s Double |  | 7 | nr | 1750 | 12250 |  | Rate Includes:Standard fire doors; cellular core; softwood lining; softwood architrave; aluminuim ironmongery (lockable, self-closure); painting or polishing; double leaf; Oak veneered; 60 min fire resistance; polished
3 | INTERNAL FINISHES | [5 empty] | 262266.883
3.1 | Wall finishes
Finishes to walls and columns: details to be stated.
| Paint finish |  | 2361.33 | m2 | 5.1 | 12042.783 |  | Rate Includes: insitu wall finishes, one miss coat and two coats of emulsion. Rate is the highest value to relfect current market conditions
3.2 | Floor finishes
| Finishes to floors: details to be stated. | [6 empty] | drawing (carpet everywhere, vinyl in wetrooms)
| Vinyl to floors to circulation space, wet areas and stairs |  | 500.7 | m2 | 59 | 29541.3 |  | Rate Includes: Flexible tiling; welded sheet or butt joint tiles; adhesive fixing vinyl safety flooring; 2.00–2.50 mm thick.
| Resin paint to floor |  | 0 | m2 | 0 | 0
| Carpet to apartment floors |  | 0 | m2 | 0 | 0
| Carpet, higher specification to circulation and classroom areas |  | 2023.38 | m2 | 60 | 121402.8 |  | Rate Includes: Carpet tiles; including underlay, edge grippers heavy domestic duty; to treads and risers; PC Sum £38/m2
3.3 | Ceiling finishes
Finishes to ceilings: details to be stated.
| Plasterboard to soffit |  | 2720 | m2 | 36.5 | 99280 |  | Rate Includes: Plasterboard to sofits 9 mm Gyproc board and skim coat
| Decoration |  |  |  |  | 0
4 | FITTINGS AND FURNISHINGS | [5 empty] | 0
4.1 | General fittings, furnishings and equipment
Kitchen units: details to be stated.
| Kitchens |  | 0 | no | 0 | 0
5 | SERVICES | [5 empty] | 2292504.75
5.1 | Sanitary installations
Sanitary appliance: details to be stated.
| WC Installation |  | 14 | no | 460 | 6440 |  | Rate Includes: Sanitary fitting W/C Suite Based on secondary school block
| WC Sink installation |  | 14 | no | 330 | 4620 |  | Rate Includes: Wash hand basin Based on secondary school block
| baths including bath panels & trims - N/A |  | 0 | no | 0 | 0
0
5.3 | Disposal Installations
Drainage to sanitary appliance: details to be stated.
| Generally |  | 2681.75 | m2 | 25 | 67043.75 |  | Rate Includes: Disposal Installations, waste soil and vent installation; uPVC pipe work and fittings Based on secondary school block
5.4 | Water installations
Mains water supply: details, including the number of draw-off points (nr), to be stated.
| Cold & hot water |  | 2681.75 | m2 | 29 | 77770.75 |  | Rate includes: Disposal Installations. Hot and cold water supply. Based on secondary school block
5.5 | Heat source
Heat source (nr): details, including output of heat source (kW), to be stated.
| Boilers + Radiators |  | 2681.75 | m2 | 180 | 482715 |  | Rate Includes : Space heating, all costs associated with the supply and installation of the heating system, temperature control and distribution pipework
5.8 | Electrical installations
Power & Data distribution
| Distribution boards and sub-mains |  | 2681.75 | m2 | 20 | 53635 |  | Rate includes: Electrical and Gas Installations. Distribution boards and sub-mains.
| General Power Installation |  | 2681.75 | m2 | 59 | 158223.25 |  | Rate includes: Electrical and Gas Installations. General power distribution
| General lighting Installation |  | 2681.75 | m2 | 120 | 321810 |  | Rate includes: Electrical and Gas Installations. General lighting distribution
| Solar PV Panels |  | 387 | m2 | 1225 | 474075 |  | Rate Includes: Solar PV systems: Residential solar water heating including collectors; dual coil cylinders; pump; controller
5.1 | Lift and Conveyor installations
Passenger lifts: details, including capacity (i.e. number of persons), speed (in m/sec), number of doors (nr), door heights and number of levels serviced (nr), to be stated.
| Passenger lift |  | 2 | no | 130000 | 260000 |  | Rate Includes: Passenger lifts (standard brushed stainless steel finish; 2 panel centre opening doors) 13-person; 6 stops; 1.6 m/s speed
5.11 | Fire and lightning protection
| Fire and Lighting Protection |  | 2681.75 | m2 | 22 | 58998.5 |  | Rate Includes: Lighting protection and sprinklers. Based on an office building
5.12 | Communication, security and control systems
Telecommunication systems: details of each type of system to be stated.
Data transmission systems: details of each type of system to be stated.
| Fire Alarm Installation |  | 2681.75 | m2 | 22 | 58998.5 |  | Rate is based on a Secondary School Block
| Intruder Alarm Installation |  | 2681.75 | m2 | 21 | 56316.75 |  | Rate is based on a Secondary School Block
| Data Installation |  | 2681.75 | m2 | 22 | 58998.5 |  | Rate is based on a Secondary School Block
| CCTV Installation |  | 2681.75 | m2 | 24 | 64362 |  | Rate is based on a Secondary School Block
| Door Access Installation |  | 2681.75 | m2 | 33 | 88497.75 |  | Rate is based on a Secondary School Block
8 | EXTERNAL WORKS - N/A | [5 empty] | 287250
8.1 | Site Preparation works | [6 empty] | Works are not applicable due to insuffecient information to price on drawings
| See above |  |  |  |  | 0
8.2 | Roads, Paths, pavings and surfacings | [6 empty] | Works are not applicable due to insuffecient information to price on drawings
Roads: details, including width, to be stated.
| Tarmacadam to road and parking spaces |  | 0 | m² | 0 | 0
| Edgings |  | 0 | m | 0 | 0
8.3 | Soft landscapes, planting and irrigation systems | [6 empty] | Works are not applicable due to insuffecient information to price on drawings
Grassed areas: details to be stated.
| soft landscaping |  | 0 | m² | 0 | 0
8.4 | Fencing,railings and walls | [6 empty] | Works are not applicable due to insuffecient information to price on drawings
Walls: details, including height (m), to be stated.
| 2.1 High brick boundary wall |  | 0 | m | 0 | 0
Fencing: details, including height (m), to be stated.
| 2.1 High timber boundary fence |  | 0 | m | 0 | 0
Gates: details to be stated.
| Electric access gates |  | 0 | nr | 0 | 0
8.6 | External Drainage | [6 empty] | Works are not applicable due to insuffecient information to price on drawings
| Drainage allowance |  | 0 | nr | 0 | 0
8.7 | External Services | [6 empty] | Works are not applicable due to insuffecient information to price on drawings
Electrical
Connections to statutory undertaker's electricity main: details to be stated.
| Main electrical supply |  | 1 | item | 76500 | 76500 |  | Rate Includes: Electric main; all laid in trenches including excavation and backfill with excavated material 600/1000 volt cables. Two core 25 mm dia. cable including 100 mm dia. clayware duct. Including subsation and Connection.
Water
Connections to statutory undertaker's water main: details to be stated.
| Water mains supply |  | 1 | Item | 74500 | 74500 |  | Rate Includes: Water Mains Supply. Water main; all laid in trenches including excavation and backfill with excavated material up to 50 mm dia. MDPE pipe. Inc service connection charges
Gas
Connections to statutory undertaker's gas main: details to be stated.
| Gas Mains Supply |  | 1 | Item | 120000 | 120000 |  | Rate Includes: Gas Main Supply. Gas main; all laid in trenches including excavation and backfill with excavated. Including connection. material. 150mm dia. Gas pipe
Street Lightning
External lighting to pedestrian areas: details to be stated.
| Works Allowance |  | 1 | item | 16250 | 16250 |  | Rate Includes: Lighting to pedestrian areas an estate roads on 4.00 m–6.00 m columns with up to 70 W lamps
9 | MAIN CONTRACTOR'S PRELIMINARIES | [5 empty] | 447435.7673
| Main contractors preliminaries & OHP |  | 10 | % | 4474357.6726 | 447435.7673
| SECTION SUB-TOTAL | [5 empty] | 5220589.3199
4094.5799