Charity dinner to build a hospital in Abuja, Nigeria South Africa.

London Marriott Hotel County Hall

Event Log

| Student Name: | Hasan Mangov-1815075 |
| --- | --- |
| Responsibility | Marketing Manager |

|  | Role of Marketing Manager |
| --- | --- |

Marketing Director is the one that treats him as a link between the department and the General Management. Well, following the line of this thought, the first function that a Marketing Director has is to transform all the outputs of his department into a simple and complete speech. in such a way that the General and Executive Management can understand at a glance how the department works, who it is in charge of each task, what results have been obtained from the campaigns carried out and what problems exist, if any. The communication function is the first because it is a transversal task that all department directors must be clear about, but, in our opinion, the most important function for a Marketing Director is to propose the Marketing Plan. The Marketing Plan is a document that is responsible for defining the outcomes of the charity event. Marketing plan is based on analysis of the situation, the objectives of the department for the event, the resources we have, the action plan (which basically establishes the objectives and gives them a date, person responsible and method of action) and the control tools. The Marketing Plan is not only about establishing the objectives and resources to be used, it is also (and, in fact, it is the most important part) implementing everything discussed in the document. Therefore, another function that the Marketing Director have will be to turn each objective into a well-defined strategy that gives the department everything necessary to achieve what is proposed at the start of event planning. The toughest task that the Marketing Director will have to face will be to move the optimistic objectives and the highly optimized resources to the daily activity.

| Week 1 | Monday July 20th, 2020 |
| --- | --- |
| Target | Analyse the possible marketing Platforms |
| Planning: - Understand the purpose of event - Communicate with team members - Approach media channels - Evaluate social media platforms for advertisement campaign - Setting tasks for every week to meet the deadline |  |
| Organising: - Divide the marketing processes into smaller fields - Determine responsibilities of team members - Distribute tasks according to individual capabilities - Set marketing targets and strive to achieve them |  |
| Managing: - Setting Giant Chart to evaluate the progress - Calculate total available time and manage the advertisement to get maximum audience - Communicate with Finance manager and Event manager for advertisement platform selection. |  |
| Marketing: - To define possible marketing strategies. - To communicate with rest of the team. - Evaluate social media platforms including Facebook, Instagram, Twitter, etc. - Define target audience - To provide possible designs of advertisement posters - Innovate and design marketing content for the website - Defining facts and need of hospital in Nigeria South Africa - Innovate marketing ideas to get maximum public attention |  |
| Technical: - Assisting in identification of audience - Assisting in emerging alternatives and options - Assisting in print media and digital advertisement - Assisting in evaluating, selecting, and refining marketing platforms and options - Assisting in the formation of the final recommendation |  |
| Problems/Resolution Action Plan: - As a first week of the project, the marketing manager and team have no clear image about marketing goals - Team members are selected on the base of leader choice, that may affect the work progress - Marketing of charity event include different domains like social media, letters and mails, invitations, print and press media. - group review Mondays weekly and teams to agree on individual meeting days. - Discuss the pros and cons of adopting any marketing strategy |  |
| Focus for the Week: - Brainstorming on how to get maximum charity with minimum expense on marketing - Compare different social media platforms to evaluate which platform is best to launch marketing campaign. - Divide marketing tasks in team members. - Marketing theme to be discussed. |  |

Student Signature: Hasan Mangov Date: 20/07/20

| Week 2 | Monday July 27th, 2020 |
| --- | --- |
|  | Strategic marketing plans |
| Planning: - Defining a marketing plan for event - Strategic layout of market plan - Theme planning - Identification of individual roles in team |  |
| Organising: - Digital marketing strategy is formulated to attract target audience - Selection of social media platforms and targeted audience - Newsletter and print media strategy - Data record lists for invitations and marketing campaign |  |
| Managing: - Communicate with team members to select best marketing strategy for event - Daily meeting and data sharing for innovative marketing ideas - Communicate with event manager and F&B coordinator for charity promotion at county hall - Evaluate the progress by following giant chart |  |
| Marketing: - For the marketing strategy of event, it is important to consider the digital marketing - Marketing strategy is aimed to highlight the event at international level. - Marketing team contact global NGO’s and health providers to promote the event and support us in charity event. - Website theme of the event is selected |  |
| Technical: - Different social media platforms are of different nature like Instagram is focused toward fashion and beauty and twitter is for short length quotes. Choice of digital platform for charity promotion is technical. Logo samples were designed. - While formulating marketing strategy, selection of targeted audience may affect the purpose of event. - Assign tasks according to capabilities of individual - Marketing staff may not expert in website and digital troubleshooting, they require technical support to resolve technical issues |  |
| Problems/Resolution Action Plan: - Meetings are not as effective as it should be, because of personal issues and difference - Lack of communication between team members - Different point of views of team members that oppose each other - To solve the communication problems and personal issues, decision making process is based on voting. |  |
| Focus for the Week: - This week is focus on strategic planning of advertisement campaign. - Digital marketing of event - Importance of attendance from all team members. - Marketing team to Goals: deciding on strategy, marketing scheme and email list to maximize the popularity of event. - Consider creating an e-mail list to create publicity ready for website |  |

Student Signature: Hasan Mangov __________________________________ Date: 27/07/20 _________________________________

| Week 3 | Monday August 3th, 2020 |
| --- | --- |
|  | Design invitations, flyers and advertisements |
| Planning: - Development of content for advertisement. - Design flyers - Design email invitations for guests - Social media advertisement - Invitations to global health and charity organizations |  |
| Organising: - Follow giant chart for progress evaluation - Distribution of responsibilities - Develop marketing content - Meet deadlines - Launch advertisement campaign - Getting global attention |  |
| Managing: - Manage advertisement content to make a sense - Manage team performance - Discussed marketing team responsibilities - Manage overall progress of marketing processes |  |
| Marketing: - Marketing team develop posters, flyers and advertisement content. - Update the website accordingly to get audience attention - Marketing staff to work, create promotional content using different software - Design Email invitations to the guest list. - Social media content including purpose and need of building a hospital - Content development for colleges, universities, NGO’s, charity organizations - Written articles to be publish at website and other media platforms |  |
| Technical: - Content development require skills and marketing of developed content is also technical. - Getting more visitors on website require SEO tools and marketing manager is responsible for accurate execution of planned strategy - Develop all the content in form of videos and upload them on YouTube channel. - Designing flyers and advertisement must be well aligned with event theme |  |
| Problems/Resolution Action Plan: - Initially one email template was designed, it is not feasible to ask everyone in a same way. Guest list was divided into different categories like NGOs, Professors, etc. different emails were designed for each category. - More effective communication and deadlines were set for this week are met. |  |
| Focus for the Week: - This week is based on content development for advertisement of event - Flyers are designed and ready to publish - Website content including images, videos, written articles, posters, audio messages etc are ready in this week - Newsletter, Paper and magazine content is ready - Sample emails for different categories are ready |  |

Student Signature: Hasan Mangov Hasan Mangov __________________________________ Date: 03/08/20 _________________________________

| Week 4 | Monday August 10th, 2020 |
| --- | --- |
|  | Send Invitations, run advertisements and resolve communication issues |
| Planning: - Most important task during this week is to achieve targets, meet deadlines and work according to plan - Tasks for this week include publishing the content, attract more audience, send invitations, develop a clear communication and invite people internationally to contribute by using online payment methods. - Regularly update event and finance manager about marketing achievements and set targets. |  |
| Organising: - Publish content and invite target audience. - Meeting deadlines. - Everyone is working to achieve the targets. - Conduct meeting with event and finance manager for progress evaluation |  |
| Managing: - Record the data of advertisement and marketing campaign - Manage teamwork and advertisement load - No meeting minutes were shared with the team by the management team. |  |
| Marketing: - Update website - Send invitations - Publish call for donations at supporting organization’s websites |  |
| Technical: - Simply publishing content is not enough for the marketing, it is important to consider the response of audience and modify advertisement settings to achieve targets. - Addition of subscribers needs to improve communication with audience and record keeping |  |
| Problems/Resolution Action Plan: - Time management was a problem for marketing team, many team members spend extra hours to meet the deadlines. - Marketing team missing some meeting minutes and the minutes are not descriptive. |  |
| Focus for the Week: - This week is focused on improve communication and publishing content. - Get maximum attention from audience - Upload the profiles on the website. - Marketing team to get connected with audience - Send invitations to the guests |  |

Student Signature: Hasan Mangov __________________________________ Date: 10/08/20 _________________________________

| Week 5 | Monday August 17th, 2020 |
| --- | --- |
|  | Register charity members and make a log |
| Planning: - To maintain the user data - To Register new attendees - To Monitor online donations - To update website sections and event description as well - To record data for future utility |  |
| Organising: - Organizing meeting with marketing team to receive all the information and descriptions. - Record user information and add them to charity group, send regular news and updates. |  |
| Managing: - Manage and record the data also update website accordingly - Clear responsibilities for every team member |  |
| Marketing: - Introduction to the event - Speeches of guest speakers - Recognition from global organizations |  |
| Technical: - With global recognition, there is a heavy load on website, and it is important to list down the data of each user. - All the requirements need to fulfil - Communication with F&B coordinator and event manager to manage marketing activities. - Suggestion to add users to a pool where they can communicate and share ideas. Share regular newsletter with users. |  |
| Problems/Resolution Action Plan: - No issues |  |
| Focus for the Week: - To respond the online donations - Record data of donors - Manage the marketing activities during event - Post event data on website |  |

Student Signature: Hasan Mangov __________________________________ Date: 17/07/20 _________________________________

| Week 6 | Monday August 25st, 2020 |
| --- | --- |
| Target | Closing and Final Report |
| Planning: - Record the videos and photos for website and promotion - Analyse the response of attendees - Finalize the report for marketing management and expenses - Analyse the feedback - Register attendees to keep in touch and to join the community - Publish the recorded data |  |
| Organising: - Register attendees and send them newsletters - Organize financial report of the marketing campaign - Have a team meeting - Organize a detailed report of charity collection and value addition - Record keeping for future use |  |
| Managing: - Manage online transaction records to analyse the value addition by marketing - Manage documents and reports - Manage the registration process on website - Respond to the visitors and charity collection - Manage finalized reports |  |
| Marketing: - Publish speech of guest speakers on website and social media channels - Upload videos, photos and appealing quotes on website - Display a counter on website to show the charity amount - Articles published in newspapers, magazines and on website. |  |
| Technical: - Due to heavy traffic on web portal, server may not respond properly or get down - Handling global transactions and responding to individuals need strong coordination with team members |  |
| Closing Plan: - Being a final week, event should be summed up in the final report - Final report of the event needs to be clear, concise and complete - Financial report of the event must be delivered to the team members and other stakeholders of the event - Furthermore, for transparency, the charity records with the transactional history is to be delivered to event manager - Charity collection also needs to be analysed in the form of final report to evaluate the event success - Have a final meeting with the team to provide reports - Problems, challenges and issues must also be recorded for future events, as lesson learnt |  |
| Focus for the Week: - Focus on the event data record - Design a finalized report - Registering individuals who could contribute to charity in future - Final report must have detailed statistical analysis and graphical representation of data for better understanding - Final report must be readable for everyone include those who are not expert in marketing - Write a lesson learnt - Sum up the event with closing remarks |  |