Leading and Managing Projects (MBA)

BMMB7010

PROJECT INITIATION DOCUMENT (PID)

Name: Sharifah Wahyu binti Syed Hilal

Student ID: 1905465

Name: Sharifah Wahyu binti Syed Hilal

Name of Organisation: Yu Daily Shop

Aim of project:

In no more than twenty words, stated the overall aim of the project.

The aim of this project is to start up own business that focuses on selling handcrafted products to younger generations.

Objectives of project:

Lists up to four objectives that are each directly from the project aim. The objectives should be S.M.A.R.T (specific, measurable, achievable, realistic, time bound).

- To be doing a proper research market in term of the handcraft products, especially bags among youth

- To investigate the practicality of setting an online business selling handcrafted bags

- To develop a marketing strategy in promoting the business and in raising more awareness on the value of handcrafted products among youth

- To ensure that the business will be able to start commencing on 2nd March 2020

What is the business case for considering undertaking the project? Justify how achieving the project aim will advantage and benefit the business and its stakeholders.

The reason for starting the project is to develop the interest as an entrepreneur. Not just that, it is also to make use of the skills in producing handcrafted bags with designs that will peak interest among youth. Even though the young generation are slowly showing interest in DIY projects, but the generations finds it hard to appreciate handcrafted projects with high price range from other handcrafted entrepreneur (Staff, 2019). The reason being is that millennial are always influenced by price of the product when shopping over the quality of product and efforts of the entrepreneur.

Therefore, the costing of one bag needs to be calculated properly in order to achieve high profit that is equal to the effort and time being used. It is also important to ensure that the price is affordable and reasonable enough for youth to purchase the products (BDC, nd).

By focusing on the aim of the project, it is hope to create even more awareness in youth that handcrafted products has its values as well and will continue to enjoy and appreciate the uniqueness of handcrafted products even more. The reason being is that not all handcrafted products are produced the same as different products will achieve different outcome. Thus, it makes it different for each product. On the other hand, as the business starts to bloom, it will allow more and other products to be added in the business.

Identify the risks associated with the project and how these could be overcome

Without a doubt starting a business whether online or offline has its risk.  Therefore, there is a high probability that the sale of the product wont be going as plan. The reason being is that handcrafted products or even arts are not always priced at a low price. The reason is that the artist or entrepreneur will consider the effort and time spent on a product, which is essential when doing such business or selling the products (Adam, 2013). Due to this risk, it can create more cost than profit. Therefore, instead of putting the price up high in the early beginning, it would be better to place the price based on cost plus pricing and value-based pricing. Cost plus pricing is the adding up of costs and mark up the price accordingly, while value-based pricing is putting the price centered on how much the shopper is willing to pay depending on the worth of the product (BDC, nd).

Other than that, there is also a possibility that the selling period doesn’t begin on time due to the time constraint of getting the product done. This is because, handcrafted business requires a lot of time in order to create a few numbers of products to sell, especially the ones that requires more time per product. Therefore, it would be better to spend extra time of specific tasks in order to get the products out in time (Joe, nd). Not just that, it will also provide reassurance to the seller and will provide comfort that the project will be done in time. Hence, will provide good results.

Another possible risk that can be considered is over marketing of the product, which can cause overflowing project when the business is a one-person business. One of the few ways to avoid over market is by using the right promotion tool as a marketing method (Vasilev, 2017). It is also important to try not over market the business.

List the resources you will need to make your project a success. These may include people, time, cash, technology, and data. Say why you need them and identify any constraints that you may encounter and explain how you would overcome these.

There are a few resources that are being considered for this project to be a success, which is time, cash, technology and data.

Data: The market for this business is being targeted to young people, as that is the aim of the business.

Technology: The business will be an online business, which will be conducted in social media (Instagram) and handcrafted marketplace (Etsy.com). There are a high number of Instagram user in Malaysia, especially among the millennial (Napoleon Cat, 2019). While Etsy will provide a great number of exposures as it has millions of buyers (Carney, 2019).

Cash: In order for the business to proceed, an initial fund is required for the materials required in producing the products. The estimation funding is at £100 to start up the business.

Time: For the business to start selling its product, the business requires at least around three months to be fully ready to start its business as producing the product requires at least one month.

If primary research is involved, state what method you intend to use to collect your primary data. Outline why a particular research method was chosen over alternatives.

For this project, no primary research will be used. This is because some of the data required has been looked at and asked around in between the targeted market before. Therefore, most of the resources will be based on secondary data, which includes book referencing, journals and websites.

Operationalisation

Give a brief outline how you will operationalise this project, including a rationale for a project management approach if appropriate, and as a minimum an appropriate time and task plan.

Figure 1 shows the brief timeline of how the project will be approach in its step, accordingly.

| Task | Specific Task | Dates | Total Days |
| --- | --- | --- | --- |
| Research Market |  | 1/12/2019 – 4/12/2019) | 4 Days |
| Business Planning | Setting Up Social Media Account (Instagram, Etsy) | 5/12/2019 | 5 Days |
|  | Research on Material | 5/12/2019 – 8/12/2019 |  |
|  | Research on Registration | 8/12/2019 |  |
| Finance and Cost | Determine and Calculate Cost Materials | 10/12/2019 – 12/12/2019 | 3 Days |
| Brand Registration |  | 13/12/2019 | 1 Day |
| Production | Creating Design | 13/12/2019 – 15/12/2019 | 29 Days |
|  | Embroidering Design on Fabric | 16/12/2019 - 4/1/2020 |  |
|  | Sewing the Bags | 8/2/2020 – 11/2/2020 |  |
|  | Take Picture of Product for Content | 12/2/2020 – 13/2/2020 |  |
| Promotion / Marketing | Advertise on Social Media | 14/2/2020 – 28/2/2020 | 21 Days |
|  | Using Promotion Tool on Etsy | 2/3/2020 – 5/3/2020 |  |
| Commence Sale |  | 2/3/2020 |  |

Table 1: Business Plan with Specific Planning and Date for Timeline Chart

Figure 1: Timeline of the Business Plan

Reference

Adam, G. (2013) Why is Art So Expensive? [online] BBC. Available at: http://www.bbc.co.uk/culture/story/20130417-why-is-art-so-expensive [Accessed 30 Nov. 2019]

BDC. (nd). How to Price Your Product: 5 Common Strategies. [online] BDC. Available at: https://www.bdc.ca/en/articles-tools/marketing-sales-export/marketing/pages/pricing-5-common-strategies.aspx [Accessed 30 Nov. 2019]

Carney, L. (2019). Shopify vs Etsy: Should You Sell Through an Online Store or an Online Marketplace? [online] Available at: https://www.websitebuilderexpert.com/ecommerce-website-builders/comparisons/shopify-vs-etsy/ [Accessed 30 Nov. 2019]

Joe, T. J. (nd). Project Constraints: Time – How to Manage Time Constraints and Avoid Missing Deadlines. [online] Bright Hub PM. Available at: https://www.brighthubpm.com/project-planning/9230-time-as-a-project-constraint/ [Accessed 30 Nov. 2019]

Napoleon Cat. (2019). Instagram Users in Malaysia. [online] Napoleon Cat. Available at: https://napoleoncat.com/stats/instagram-users-in-malaysia/2019/10 [Accessed 30 Nov. 2019]

Staff, H.(2018).The Millennial Consumer: How They Shop and Why They Buy. [online] Herosmyth. Available at: https://www.herosmyth.com/article/millennial-consumer-how-they-shop-why-they-buy [Accessed 30 Nov. 2019]

V. (2017). Over Marketing, What It Is and Why You Should Be Careful With It. [online] Wealth Magnate. Available at: https://wealthmagnate.com/over-marketing-what-it-is-and-why-you-should-be-careful-with-it/ [Accessed 30 Nov. 2019]