## Cost Plan (plus)
RIBA Work Stage C: Concept Design
Elemental Cost Plan 1 (Plus)
(Compatable with NRM2 BoQ Summary Template)
Cost Centre | Group Element/Element | Element Unit Quantity (EUQ) | Element Unit Rate (EUR) | Cost target of element (= EUQ x EUR)
Tender Price Index (TPI): |  | m² | £ | £
Location Factor (LF):
Building Works
0 | Facilitating works |  | 0 | 0
1 | Substructure | 500 | 1000 | 500000
2 | Superstructure | 1000 | 1500 | 1500000
3 | Internal finishes |  | 0 | 0
4 | Fittings, furnishings & equipment |  | 0 | 0
5 | Services |  | 0 | 0
6 | Complete buildings & building units |  | 0 | 0
7 | Work to exisiting buildings |  | 0 | 0
8 | External works |  | 0 | 0
Sub Total: Facilitating & Building Works (A) |  |  |  | 2000000
9 | Main Contractors Preliminaries (B) | 25 | % | 500000
Sub Total: Facilitating & Building Works (including MC Preliminaries (C) [C = A + B] |  |  |  | 2500000
10 | Main Contractors overheads & profit (D) | 10 | % | 250000
Total: Building works estimate (E) [E = C + D] |  |  |  | 2750000
Project and design team fees and other development and project costs
11 | Project & Design team fees (F) | 500 | 100 | 50000
12 | Other development & Project Costs (G) | 500 | 50 | 25000
Total: Project and design team fees and other development and project costs estimate (H) [H = F + G] |  |  |  | 2825000
| Base Cost Estimate (I) [I = E + H] |  |  | 5575000
13 | Total: Risk allowance estimate (J) | 0 | % | 0
| Cost Limit (excluding inflation) (K) [K = I + J] |  |  | 5575000
14 | Total: Inflation allowance if not using TPI above (L) | 10 | % | 557500
15 | Cost Limit (excluding VAT assessment) (M) [M = K + L] |  |  | 6132500
16 | VAT assessment (excluded normally) |  |  | 6132500