# BIM Execution Plan

BIM BEP - SA1 Olympic Pool/ Leisure Complex

For University of Wales Trinity Saint David (UWTSD)

| Date: | 3 May 2023 |
| --- | --- |
| Doc ref: | BWG-ACTIV-XX-XX-RP-Z-0000_S2_P02 |

Document Control Sheet

| Issued by | Activ Leisure Construction Ltd. Swansea, United Kingdom | Office contact Info@Activ-Leisure-Construction.co.uk |
| --- | --- | --- |
| Client | University of Wales Trinity Saint David (UWTSD) |  |
| Project name | BIM Execution Plan |  |
| Title | BIM BEP - SA1 Olympic Pool/ Leisure Complex |  |
| Doc ref | BWG-ACTIV-XX-XX-RP-Z-0000_S2_P02 |  |
| Project no. | 0023 |  |
| Status | S2 |  |
| Date | 03/05/2023 |  |

Document Production Record

| Issue Number | P02 | Name |
| --- | --- | --- |
| Prepared by |  | Jon Langstone |
| Checked by |  | Cam Evans, Toby Adamson, Chris Atkinson, Jenny Stroud |
| Approved by |  | Gavin Traylor, Allan Nantel, Deborah Hughes, |

Document Revision Record

| Issue Number | Status | Date | Revision Details |
| --- | --- | --- | --- |
| P01 | S2 - Information | 12/12/2016 | First shared issue |
| P02 | S2 - Information | 20/01/2020 | Updated for BS EN ISO 19650 Guidance |

Activ' Leisure construction limited has prepared this report in accordance with the instructions of the above-named client for their sole and specific use. Any third parties who may use the information contained herein do so at their own risk.

Contents

1.	Introduction	2

1.1	Table of Abbreviations	3

2.	Information Requirements	4

2.1	Asset Information Requirements (AIR)	4

2.2	Project Information Requirements (PIR)	4

2.3	Exchange Information Requirements (EIR)	4

3.	PROjECT Management	6

3.1	Roles, Responsibilities and Authorities	6

3.2	Major Project Milestones	7

3.3	Project Information Model Delivery Strategy	8

3.4	Approval of Information	9

4.	Planning and Documentation	9

4.1	Agreed Project Processes for collaboration and information modelling	11

4.2	Classification	12

4.3	Agreed Matrix of Responsibilities across the supply chain	13

5.	Standard method and procedure	1

5.1	File naming convention	1

5.2	Layer Naming Convention	5

5.3	Drawing sheet templates	5

5.4	Annotations, dimensions, abbreviations, and symbols	6

5.5	Provision of Common Data Environment	6

5.6	IT Software versions	7

6.	References	7

# Introduction

This document, created by Activ Leisure, should be read alongside the contract documents issued by or on behalf of the client as part of the tender process. Its purpose is to outline the obligations, usage, and delivery of BIM throughout the project's design, construction, operation, and maintenance stages, in accordance with national and international BIM standards. This will facilitate collaboration and align with the UK BIM Framework.

To create this BEP template, we have used the CPIC BEP template document [2] as a basis and adapted it to meet the specific requirements of this project.

For existing projects that adhere to the superseded PAS 1192-2 and BS 1192 standards without contractual obligation, they can continue without changes. However, if an appointed party chooses to transition to the ISO 19650 series, they must assess the impact of the transition in terms of capability, upskilling needs, risk of change, and transitional costs. Typically, the transition should occur at the beginning of a project stage (e.g., concept design, developed design, construction, in use), and the earlier it happens in the project lifecycle, the smoother the transition will be.

This BIM Execution Plan incorporates the following standards:

BS 1192:2007+A2:2016 - Collaborative production of architectural, engineering and construction information – Code of practice.

PAS 1192-2:2013 - Specification for information management for the capital delivery phase of construction projects using BIM.

PAS 1192-3 - (ISO 19650-3 at comment stage) - Specification for information management for the operational phase of assets using BIM.

BS 1192-4 - (ISO 19650-4 proposed) - Collaborative production of information: Fulfilling employer’s information exchange requirements using COBie – Code of practice.

PAS 1192-5 - (ISO 19650-5 at comment stage) - Specification for security-minded BIM, digital built environments, and smart asset management.

BS 7000-4 - Design management systems: Guide to managing design in construction.

BS 8541 - Library objects for architecture, engineering, and construction

PAS 91 - Construction prequalification questionnaires

BS EN ISO 19650-1:2018 - Organization and digitization of information about buildings and civil engineering works, including building information modelling (BIM) – Information management using building information modelling - Part 1: Concepts and principles.

BS EN ISO 19650-2:2018 - Organization and digitization of information about buildings and civil engineering works, including building information modelling (BIM) – Information management using building information modelling - Part 2: Delivery phase of the assets.

## Table of Abbreviations

Table 1 : Abbreviations

| Abbr. | Description |  |  |
| --- | --- | --- | --- |
| AIR | Asset Information Requirements | BEP | BIM execution plan |
| BIM | Building information modelling | CDE | Common Data Environment |
| LD | Lead designer | EIR | Exchange Information Requirements |
| PDM | Project delivery manager | PIM | Project information model |
| MIDP | Master Information Delivery Plan | TIDP | Task Information Delivery Plan |
| LOD | Level of Definition | WIP | Work in progress |
| LOMD | Level of Model Detail | LOMI | Level of Model Information |
| Cobie | Construction Operations Building Information Exchange | RFI | Request for Information |
| CPIx | Construction Project Information Exchange |  |  |
| CPIC | Construction Project Information Committee |  |  |
| OIR | Organisational Information Requirements |  |  |

Table 2: Project Information

| Project Name | SA1 Leisure Complex with Olympic Pool |
| --- | --- |
| Project Address | Port Tennant, Swansea SA1 1LY |
| Project Number (Clients Project Number or reference) | 001 |
| Contract Form | NEC Design & Build |
| Project Design Start Date | 03/10/22 |
| Project Construction Start Date | 31/05/23 |
| Project Completion and Handover Date | August/2024 |
| Project Description | Sports Leisure Complex (Olympic Pool included) |

# Information Requirements

As required by the EIR, this section of the BEP provides details of our proposals for managing the modelling, co-ordination, and collaboration processes. Reference is also made to the other sections of this BEP, where further information is provided in response to the EIR.

## Asset Information Requirements (AIR)

The AIR requires the organisation to classify the data and information being put into the Asset Information Model (AIM) according to an agreed classification system or through structures of the data store and or file store. The AIR defines the data and information required throughout the asset lifecycle and needs to be sufficient at each stage of the asset's lifecycle.

## Project Information Requirements (PIR)

As defined by BS EN ISO 19650-1:2018 Clause 5.4, PIR explains the information needed to answer or inform high-level strategic objectives within the appointing party in relation to a particular built asset project. PIR are identified from both the project and asset management processes.

## Exchange Information Requirements (EIR)

Clause 5.1 lists the following activities that should be considered in the BEP through the relevant sections:

•	Appoint individuals to undertake the information management function.

•	Establish the project's information requirements.

•	Establish the project's information delivery milestones.

•	Establish the project’s information standard.

•	Establish the project's information production methods and procedures.

•	Establish the project’s reference information and shared resources.

•	Establish the project's common data environment.

•	Establish the project's information protocol.

Weekly BIM coordination meetings will be held throughout the design and construction stages of the project. Each meeting will involve all parties responsible for information production at that stage and will include a model review and a discussion to allow each discipline to provide updates on their progress. Meeting minutes will be recorded for each meeting.

A plan of BIM meetings is provided in table 3 below.

Table 3: Meeting Procedures

| Meeting type | Project stage | Frequency | Participants | Location |
| --- | --- | --- | --- | --- |
| BIM requirements kick off | Organizational | Once | Client & Activ Leisure | TBC |
| BIM execution plan demonstration | Brief | Once | Client & Activ Leisure | TBC |
| BIM coordination | Concept, Definition, Design | Weekly | Activ Leisure designers. Do you mean the design team? Activ Leisure may not be the only designer | TBC |

Table 4: Model Delivery - Schedule of information exchange for submission and approval:

|  | File Sender | File Receiver | One-Time Or Frequency | Due Date Or Start Date | Model File | Model Software | Native File Type | File Exchange Type |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Design Authoring – 3D coordination | Design Manager | Task Team Manager | BI-WEEKLY | 23/12/22 | ARCH | REVIT | .RVT | .RVT .NWD .IFC |
| Design Authoring – 3D coordination | Structural Engineer | Task Team Manager | BI-WEEKLY | 23/12/22 | STRUCT | REVIT | . RVT | . RVT .IFC |
| Design Authoring – 3D coordination | Mechanical Engineer | Task Team Manager | BI-WEEKLY | 23/12/22 | MECH | REVIT | . RVT | . RVT .IFC |
| Design Authoring – 3D coordination | Electrical Engineer | Task Team Manager | BI-WEEKLY | 23/12/22 | ELEC | REVIT | . RVT | . RVT .IFC |

Table 5: Typical Model Exchange

| F | M | T | W | T | F | M | T | W | T | F |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Model Upload |  |  |  |  |  |  |  |  |  |  |
|  | Clash Check/ Report | Clash Det. Workshop | Actions & Report |  |  |  |  |  |  |  |
|  |  |  | Resolve/Develop/smaller workshop to resolve issues. Design Team Meeting |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Model Upload |

# PROjECT Management

This section of the BEP covers the requirements of BS EN ISO 19650 relating to the management processes that satisfy the Asset Information Requirements (AIR), Project Information Requirements (PIR) and Exchange Information Requirements (EIR).

## Roles, Responsibilities and Authorities

Table 6 records the names and contact details of the appointed party fulfilling the necessary function to make up the delivery team. All appointed parties are as defined in Appendix A.

| Role | Name (Activ Leisure Staff) | Email Telephone number |
| --- | --- | --- |
| Construction/BIM Manager | Jon Langstone | J.Langstone@activLeisure.co.uk |
| Project Manager | Chris Atkinson | C.Atkinson@activLeisure.co.uk |
| Design/BIM Manager | Cameron Evans | C.Evans@activLeisure.co.uk |
| Quantity Surveyor | Toby Adamson | T.Adamson@activLeisure.co.uk |
| Commercial Manager | Jenny Stroud | J.Stroud@activLeisiure.co.uk |

The task team members of the different functions related to production and management of information are given in Table 7.

| Role | Authority |
| --- | --- |
| Project Manager (Typically the client’s Project Manager) | Confirming resource availability and capability in relation to the responsibility's matrix issued as part of EIR. Identifying training and education needs. Collaborating to develop MIDP with reference to the team members TIDPs. Managing the delivery of information during the project (time scheduling delivery using MIDP. Supervising preparation of documentation for contracts etc. |
| Project Information Manager | Facilitating the management of the federated model and the production of project outputs. Managing the operation, standards and culture of the CDE. Authorized to enforce the Project BIM Standard and ensure delivery of the information requirement in the EIR. |
| Design Manager (Cameron Evans) | Authorized to approve the issue of design information from the WIP area of the CDE to the SHARED area. The LD’s coordinated delivery of all design information can run in parallel to the PDM’s coordinated delivery of supporting documents. Authorized to enforce spatial coordination. |
| Task Team Manager (Jon Langstone) | Authorized to enforce documentation standards within the task team. Authorized to sign-off design outputs and information related to a discipline-specific, package-based or time-based task within the WIP area of the CDE and submit to the lead designer (for review and approval from the WIP area to the SHARED area of the CDE). |
| Task Team Information Manager (Jon Langstone) | Reject non-compliant models, drawings & documents confirming that information is suitable for issue within CDE. Directing the production task information in compliance with standards and methods |
| BIM Coordinators (Jon Langstone & Cameron Evans) Typically a task team BIM technician, or lead technician on a large project | Managing spatial co-ordination on behalf of a task team. Proposing resolutions to co-ordinate clashes. |
| BIM Author (Jon Langstone) typically a task team technician or technicians | Develop constituent parts of the information model in connection with specific tasks (ownership of model information) |

Table 7

## Major Project Milestones

Table 8 is used to record the major project milestones. A more detailed and co-ordinated TIDP/MIDP is provided in Appendix B/D respectively and a Project Plan (typically a construction programme produced by the main contractor) must be developed and agreed with the stakeholders and appointing party.

Table 8 – Major project milestones

| Project phase / milestone | Estimated/ Actual start date | Estimated/ Actual completion date | Project stakeholders involved |
| --- | --- | --- | --- |
| Project brief | 03/10/22 | 22/12/22 | All disciplines |
| Concept | 23/12/22 | 27/03/23 | All disciplines |
| Definition | 23/12/22 | 27/03/23 | All disciplines |
| Design | 28/03/23 | 02/05/23 | Activ Leisure Design team |
| Build and Commission | 31/05/2023 | 26/06/24 | Activ Leisure - Contractor |
| Handover and close-out | 11/06/24 | 19/06/24 | UWTSD + Activ Leisure + Contractors |

## Project Information Model Delivery Strategy

Table 9 – Strategy for information delivery

| Priority (HIGH/ MED/ LOW) | Goal description | Potential BIM uses |
| --- | --- | --- |
| HIGH | Produce a clash-free BIM model with the appropriate level of detail | Design reviews, 3D coordination |
| HIGH | Reduce overall project time frame and cost, improve predictability | 3D coordination, cost estimation, 4D modelling |
| MEDIUM | Improve communication and presentation | Design Reviews, design authoring |
| HIGH | Reduce the number of RFI’s and change orders | 3D coordination, design review |
| HIGH | Create an as-built model for better Facilities Management post construction | Existing conditions modelling, 3D coordination |
| MEDIUM | Minimise construction waste | Design reviews, 3D coordination, engineering analysis, existing conditions modelling |
| LOW | Improve end-user staff training | 3D coordination |

## Approval of Information

To ensure that model files, drawing files and spreadsheet extraction are adequately checked, some form of agreed approvals process needs to be in place to enable the design teams and the contractor (or client) to approve and sign-off the development of the design information for a project and to assign responsible team members.

Table 10 – Schedule of information approval responsibilities

| Name | Role or Title | Models | Drawings | Peer Review | Lead Designer/Lead Contractor | Client Review Team |
| --- | --- | --- | --- | --- | --- | --- |
| Deborah Hughes | Client Project Manager | X |  |  |  | X |
| Gavin Traylor | Client Lead Designer | X | X |  | X | X |
| Jon Langstone | Task Team Manager |  |  |  | X |  |
| Jenny Stroud | Task Information Manager |  |  | X |  |  |
| Cam Evans & Jon Langstone | BIM Coordinator |  |  | X |  |  |
| Jon Langstone | BIM Author |  |  | X |  |  |

# Planning and Documentation

This part of the BIM Execution Plan outlines the obligations of BS EN ISO 19650 with respect to planning and documentation procedures that fulfil the Asset Information Requirements (AIR), Project Information Requirements (PIR), and Exchange Information Requirements (EIR). According to BS EN ISO 19650-1:2018, an information delivery plan is a generic term that encompasses all plans related to information delivery. Information requirements are defined to address key asset-related questions at different stages of the asset's delivery and operation to enable informed decision-making.

Figure 1 – Generic specification and planning for information delivery

The appointing party shall have regard to the effective management of information throughout the project and reflect the long-term asset information management strategy, as described in ISO 19650-1:2018 Clause 5.3, by nominating individuals from within the appointing party’s organization to undertake the information management function on behalf of the appointing party.

The appointing party shall also have regard to preparing information requirements relating to a particular built asset project as described in ISO 19650-1:2018 Clause 5.4, to answer or inform high-level strategic objectives within the appointing party.

The revised PIP confirms the capability of the supply chain. The PIP consists of the following completed CPIx documentation:

•	Supply chain capability summary form, which summarises the contents of

•	Supplier building information management assessment form(s)

•	Supplier IT assessment form(s)

•	Supplier resource assessment form(s)

The Project Implementation Plan presents the project team’s capability, competence, and experience of delivering BIM projects, comprising the following documents, which are provided in appendix B:

•	Supply chain capability summary form

•	Supplier building information management assessment forms

•	Supplier IT assessment forms

•	Supplier resource assessment forms

The project team’s resource for the project is provided in Table 12 below.

Table 12 – Supplier resource summary

## Agreed Project Processes for collaboration and information modelling

A Common Data Environment (CDE) is defined in ISO 19650-1 Clause 3.3.15. ISO 19650-1 distinguishes between a CDE workflow (i.e. the process) and the solution (the technology). This helps in understanding what a CDE is and how it plays its part.

Table 13 – Processes for collaboration and information modelling

| Company | Solution | Network | Database | File-based | Comments |
| --- | --- | --- | --- | --- | --- |
| Activ Leisure Architects | Revit 2023 | Viewpoint | Teams/Revizto | Doc. | The team must agree on the electronic and activity collaboration procedure. This includes model management (e.g., model check-out, revision procedures etc.) and standard meeting actions and agendas. |
| Activ Leisure Structures | Revit 2023 | Viewpoint | Teams/Revizto | Doc. | As comments above |
| Activ Leisure BPE | Revit 2019 | Viewpoint | Teams/Revizto | Doc. | As comments above |

The clash rendition viewer to be used across the whole project is stated in Table 14.

Table 14 - Clash Rendition Viewer

| Agreed clash rendition viewer | Version |
| --- | --- |
| Revizto | 5 |

The agreed authorisations for security and extranet access and authority to distribute documents are given in Table 15 below, which defines who is authorised to upload, download, and change information within the CDE.

Table 15 – Authorisations for security, extranet and document distribution

| Company | Authorised Manager | Authority (Upload, download, change Access/Distribution) |
| --- | --- | --- |
| Activ Leisure Architects | Cameron Evans | Download, Upload, Change Access/Distribution |
| Activ Leisure | Jon Langstone | Change Access/Distribution |
| Activ Leisure - Architects | Cameron Evans | Download, Upload, Change Access/Distribution |
| Activ Leisure – BIM Manager | Jon Langstone | Download, Upload, Change Access/Distribution |
| Activ Leisure - Consulting Engineers | Ross Varco | Download, Upload, Change Access/Distribution |
| Activ Leisure - MEP | Gary Ginge | Download, Upload, Change Access/Distribution |
| Activ Leisure – BIM Co-Ordinator | Jon Langstone | Download, Upload, Change Access/Distribution |
| Activ Leisure (QS) | Tobias Adamson & Jenny Stroud | Download, Upload, Change Access/Distribution |
| Activ Leisure – Documentation Administrator | Chris Atkinson | Download, Upload, Change Access/Distribution |
| UWTSD Management team | Gavin Traylor & Deborah Hughes | Download, Upload |

## Classification

BS EN ISO 19650-1:2018 recommends that classification is in line with ISO 12006-2. This standard defines the framework for classification systems internationally. Each country or region might have its own version aligned to this standard and in the UK this classification system is Uniclass 2015.

## Agreed Matrix of Responsibilities across the supply chain

This section of the BEP defines who models what (the BIM Authors) and to what Level of Definition (LOD) at each stage of the delivery process.

PAS1192-2 previously defines seven LODs, which do not reflect specific modelling guidelines for any particular software, but rather a generic definition of the level of model detail (geometrical), i.e. how individual objects display themselves and the level of model information that is required as a minimum to meet the AIR and EIR. The American Institute of Architects LOD specification forms a basis for clearly defining the content and reliability of building information models per object and at various stages in the design and construction process and is, therefore a good baseline to compare against.

At every stage in the project, the level of detail will be sufficient to meet the generic requirements of the project through a project plan or responsibility matrix. The LOD are classified depending on their volume of information in a scale ranging from 100 to 500 as extracted from the specification below:

Table 16: American Institute of Architects LOD specification

| LOD | DEFINITION |
| --- | --- |
| 100 | The Model Element may be geometrically represented in the Model with a symbol or other generic representation but does not satisfy the requirements for LOD 200. Information related to the Model Element (i.e., cost per square metre, tonnage of HVAC, etc.) can be derived from other Model Elements. |
| 200 | The Model Element is geometrically represented within the Model as a generic system, object, or assembly with approximate quantities, size, shape, location, and orientation. Non-geometric information may also be attached to the Model Element. |
| 300 | The Model Element is geometrically represented within the Model as a specific system, object, or assembly in quantity, size, shape, location, and orientation. Non-geometric information may also be attached to the Model Element |
| 350 | The Model Element is geometrically represented within the Model as a specific system, object, or assembly in terms of quantity, size, shape, location and orientation, and interfaces with other building systems. Non-geometric information may also be attached to the Model Element. |
| 400 | The Model Element is geometrically represented within the Model as a specific system, object, or assembly in terms of quantity, size, shape, location, and orientation, with detailing, fabrication, assembly, and installation information. Non-geometric information may also be attached to the Model Element. |
| 500 | The Model Element is a field-verified representation of size, shape, location, quantity, and orientation. Non-geometric information may also be attached to the Model Elements. |

Within the CIC/BIM Protocol 2018, Clause 4.12 requires a project team member to publish a responsibility matrix for the Level of Definition. This states the responsibility for information delivery at each stage and to what level of information is required.

Note that the CIC BIM Protocol is not aligned with ISO 19650, with its legal position currently under review.

BS EN ISO 19650-2:2018 Clause 5.1.3 states that the nature and substance of information to be delivered at each key decision point should be in accordance with the project plan. Clause 5.1.4 states that consideration needs to be given to the use of information during the operational phase of the asset.

Table 17 gives the NBS (National Building Specification) requirements from the NBS Toolkit, which can also be used as a LOD.

Table 18 below, shows the specific parameters mandatory per each Data Drops. Drop 3 and 4 at RIBA stage 4 and 6, are responsibility of the contractor.

Table 18

# Standard method and procedure

This section of the BEP covers the requirements of BS EN ISO 19650-2:2018 Clause 5.2.

## File naming convention

All project information files shall comply with the file naming convention of BS1192-2007 using the template provided in table 20.

Table 20 – Template for file naming

| Field: | Project | Originator | Volume | Level | File Type | Discipline | Number |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Code: | 6023 | ACTIV | XX | XX | K | DS | 1001 |

Each field shall be separated with a hyphen and joined together to form the file name. an example is provided in table 20.

Activ leisure's Structural engineering Drawing number 1001 located at level 01 of zone C of project ABC

See the ’BS EN ISO 19650-2:2018 National Annex’, or any Activ leisure BIM Standards for additional explanation.

### Project

Table 21 defines the project code(s) that will be used for this project:

Table 21 – Project code

| Code | Project |
| --- | --- |
| 6023 | SA1 Sport Leisure Complex (Olympic Pool) |

Where an organisation needs to use their own internal project numbers, then they can be indicated in the drawing title block using a separate ‘project number’ box.

### Originator

The following originator codes have been agreed and shall be used by the relevant parties for file naming purposes on this project:

Table 22 – Originator codes

| Code | Originator Company name |
| --- | --- |
| AT | Architect |
| CVE | Civil and Structural Engineer |
| MEP | Mechanical and Electrical Engineer |

### Level or Location

The following level or location codes have been agreed and shall be used by the relevant parties for file naming purposes on this project:

Table 24 – Level or location codes (see BS EN ISO 19650-2:2018 National Annex NA.3.5)

| Code | Level | Code | Level |
| --- | --- | --- | --- |
| GF | Ground Floor | CPL | Underground Carpark Level |
| FF | First Floor |  |  |
| SF | Second Floor |  |  |

Table 25 – Agreed file types for documents (see BS EN ISO 19650-2:2018 National Annex NA.3.6)

| Code | File Type |
| --- | --- |
| M3 | Model File (3D) |
| M2 | Model File (2D) |
| MR | Model Rendition File (for Coordination, not original format) |
| AF | Animation File |
| VF | Visualisation File |
| DB | Database |
| DR | Drawing |
| IR | Issue Register |
| PP | Presentation |
| RD | Room Data Sheet |
| SA | Schedule of Accommodation |
| SC | Structural Calculation |
| SH | Schedule |
| SK | Sketch |
| SP | Specification |

### Discipline

A list of discipline or role codes as recommended in BS EN ISO 19650-2:2018 National Annex NA 2 and NA 3 shall be used for file naming purposes, as shown in the table below.

Table 26 – Discipline codes (see BS EN ISO 19650-2:2018 National Annex NA.3.7)

| Code | Discipline |
| --- | --- |
| A | Design Manager / Architect |
| B | Building Surveyor |
| C | Civil Engineer |
| D | Drainage, Highways Engineer |
| E | Electrical Engineer |
| F | Facilities Manager |
| G | Geographical Information System Engineers and Land Surveyor |
| I | Interior Designer |
| K | Client |
| L | Landscape Architect |
| M | Mechanical Engineer |
| P | Public Health Engineer |
| Q | Quantity Surveyor |
| S | Structural Engineer |
| T | Town and Country Planner |
| W | Contractor |
| X | Sub-Contractor |
| Y | Specialist Designer |
| Z | General (non-disciplinary) |

Table 27 – Extended discipline codes for this project

| Code | Discipline |
| --- | --- |
| A1 | Project Manager |
| A2 | Construction Manager |
| A3 | Commercial Manager |

### Number

For this project, all disciplines shall use numbers conforming to the following convention:

6023-UWTSD-XX-XX-T-X-0001-XXX

### Metadata

The following metadata status codes shall be used for this project in accordance with BS EN ISO 19650-2:2018 National Annex NA.4:

Table 28 – Metadata status codes (see BS EN ISO 19650-2:2018 National Annex NA.4.2)

| Status | Description | Revision | Revision Code |
| --- | --- | --- | --- |
| “Work in progress” (WIP) |  |  |  |
| S0 | Initial status | Preliminary revision and version | P01.01, P01.02 etc |
| Shared (non-contractual) |  |  |  |
| S1 | Suitable for coordination. The file is available to be ‘shared’ and used by other disciplines as a background for their information. | Preliminary revision | P01, P02 etc |
| S2 | Suitable for information. | Preliminary revision |  |
| S3 | Suitable for review and comment. | Preliminary revision |  |
| S4 | Suitable for stage approval. | Preliminary revision |  |
| S5 | Withdrawn | N/A |  |
| S6 | Suitable for PIM authorisation | Preliminary revision |  |
| S7 | Suitable for AIM authorisation | Preliminary revision |  |
| Published (Contractual) |  |  |  |
| A1, An. | Approved and accepted as stage complete (C=Contractual/Complete) | Contractual revision | C01, C02 etc |
| B1, Bn. | Partially signed off with minor comments from the Client (clouded in abeyance) | Preliminary revision | P01.01, P01.02 etc |
| Published (for AIM Acceptance) |  |  |  |
| CR | As Construction Record documentation, PDF, models | Contractual revision | C01, C02 etc |

## Layer Naming Convention

Table 29 – BS1192 Layer naming convention

| Field | Discipline | Classification | Presentation | Description |
| --- | --- | --- | --- | --- |
| Name | A | G23 | M2 | Stairs |
| Example | Architect | Stairs (Uniclass) | Model geometrics (2D) | ****** |

2D software may be used for BIM level 2 authoring, but typically we expect 3D modelling to be the norm at this level. Therefore, all modelling and coordination should be produced using RVT, IFC and NWD formats where layer naming convention is not required.

## Drawing sheet templates

Table 32– List of drawing sheet templates

| Sheet Size | Sheet File name |
| --- | --- |
| A0 Landscape | TBC-DR-A-A0 LandscapeVerticalBlock |
| A1 Landscape | TBC-DR-A-A1 LandscapeVerticalBlock |
| A3 Landscape | TBC-DR-A-A3 LandscapeVerticalBlock |
| A0 Portrait | TBC-DR-A-A0 PortraitVerticalBlock |
| A1 Portrait | TBC-DR-A-A1 PortraitVerticalBlock |
| A3 Portrait | TBC-DR-A-A3 PortraitVerticalBlock |

Table 33 – Drawing sheet scales

| Scale | Description of detail |
| --- | --- |
| 1:1000 | 1:1000 Scale Detail shows shape and layout |
| 1:500 | "" |
| 1:200 | "" |
| 1:100 | 1:100 Scale Detail shows shape, layout, and construction elements |
| 1:50 | 1:50 Scale Detail shows how the construction elements meet at junctions |
| 1:20 | "" |
| 1:10 | "" |
| 1:5 | 1:5 Scale detail show shape, dimensions, and assembly of the separate construction elements |
| 1:1 | All model files must be modelled at 1:1 Scale |

## Annotations, dimensions, abbreviations, and symbols

To ensure accuracy and consistency, dimensions in CAD drawings should be derived automatically from the underlying CAD coordinates using the "associative dimensioning" function of CAD systems. This function ensures that the dimensions are geometrically accurate and directly related to the underlying CAD coordinates.

It is important to note that dimensions should not be entered as text, as this can compromise the relative positions of elements in the drawing.

To ensure clear communication and understanding, the project team should agree on common units of measurement for distance (such as meters and millimetres) and angles (such as degrees or radians measured clockwise or counter clockwise). This will help to avoid confusion and errors when interpreting the CAD drawings.

Table 34 – Agreed units of measurement.

| Type of information | Millimetres | Metres | Degrees | Radians |  | Clockwise | Counter |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Survey |  |  |  |  |  |  |  |
| Roads |  |  |  |  |  |  |  |
| Models |  |  |  |  |  |  |  |
| Drawings |  |  |  |  |  |  |  |

## Provision of Common Data Environment

The following common data environment solution shall be used on this project:

Table 35 - Common Data Environment Solution

| Name of the CDE | TBC |
| --- | --- |
| CDE Address | Activ Leisure ****01 |
| Document Controller | Chris Atkinson |

## IT Software versions

Each discipline shall use the agreed CAD software throughout the project as stated in the following table:

Table 36 – Agreed software versions

| Company | Database | CAD software | Version | Format | Comments |
| --- | --- | --- | --- | --- | --- |
| Activ Leisure | SQL | Revit | 2023 | RVT | TBC |
| Activ Leisure |  | Revit | 2023 | RVT | TBC |

      - Exchange formats

The agreed formats for model and drawing file exchange are:

Table 37 – Agreed exchange formats for models and drawings.

|  | DWG | DGN | DWF | PDF | IFC | Other |
| --- | --- | --- | --- | --- | --- | --- |
| Models |  |  |  |  | x | RVT |
| Drawings | x |  |  | x |  |  |
| Final drawing format | x |  |  | x |  |  |
| Schedules or spreadsheets |  |  |  | x |  | XLS |

Process and data management systems

The process and data management systems shall be described under section 3.2 Agreed project processes for collaboration and information modelling.

# References

[1]	Construction Project Information Committee (2013) ‘Pre-Contract Award Building Information Modelling (BIM) Execution Plan (BEP)’ CPIx online

[2]	Construction Project Information Committee (2013) ‘Post Contract-Award Building Information Modelling (BIM) Execution Plan (BEP)’ CPIx online

[3]	BS1192 (2007) “Collaborative production of architectural, engineering and construction information – Code of practice” BSI

[4]	PAS 1192-2 (2013) “Specification for information management for the capital/delivery phase of construction projects using building information modelling” BSI

[5]	Mervyn Richards (2010) “Building Information Management: A Standard Framework and Guide to BS 1192” BSI