## Worked Example
Worked Example
[7 empty] | 5 | 5 | 10 | 10 | 1 | 11
Procurement/ Purchasing | [6 empty] | Get estimates |  |  | Select printer
[7 empty] | 19 | 14 | 24 | 24 | 14 | 25
| 0 | 1 | 1 | 1 | 4 | 5 | 5 | 1 | 6 | 6 | 1 | 7
Marketing | Select printer |  |  | Draft layout |  |  | Select photographer |  |  | Commission photos
| 0 | 0 | 1 | 1 | 0 | 5 | 23 | 18 | 24 | 24 | 18 | 25
Critical activities are those with a zero float
[7 empty] | 5 | 10 | 15 | [5 empty] | The critical path links tasks with a zero float.
Course Leader | [6 empty] | Get testimonials
[7 empty] | 5 | 0 | 15
[10 empty] | 15 | 10 | 25 | 25 | 3 | 28 | 28 | 1 | 29 | 29 | 2 | 31
Brochure Design | [9 empty] | Write text |  |  | Finalise layout |  |  | Artwork to printer |  |  | Check proofs
[10 empty] | 15 | 0 | 25 | 25 | 0 | 28 | 28 | 0 | 29 | 29 | 0 | 31
[19 empty] | 31 | 15 | 46
Printing/ Reprographics | [18 empty] | Print 20,000 copies
[19 empty] | 31 | 0 | 46

## Stage 1
Calculating Earliest Times and Durations |  |  | Earliest Start | Duration | Earliest Finish
Task Description
|  |  | Latest Start | Total Float | Latest Finish
Example 1
1 | 3 | 4 | 4 | 2 | 6
Task X |  |  | Task Y
Normally the unit of time will be days. The project will start on day zero so the Earliest Start Time of the first task will be 0. |  |  | If there is only one task (task X) preceding task Y, then the EST of task Y = the EST of task X plus the duration of task X.
Example 2
0 | 3 | 3 | 5 | 2 | 7
Task X |  |  | Task Z
0 | 5 | 5 | The EST of task Z = the latest of the EFTs of tasks X and Y.
Task Y
The minimum project duration will be the EFT of the last task in the project.
If there are two unrelated tasks (tasks X and Y) preceding task Z, then do the same calculation for each route.

## Stage 2
Calculating Latest Times and Floats |  |  | EST | DUR | EFT
Task Description
|  |  | LST | FLOAT | LFT | The LFT is the latest time an activity can be completed without delaying the whole project.
Example 1
0 | 3 | 3 | 3 | 2 | 5 | The FLOAT of a task = LFT - (EST + DUR). It is the number of days the task can be delayed without delaying the next task.
Task X |  |  | Task Y
5 | 5 | 8 | 8 | 5 | 10 | It follows that any delay to the start date of a task uses some of this float.
To calculate latest finish times, start from the final task and work backwards through each task to the start. |  |  | If only one task (task X) directly precedes task Y, then the LFT of task X = LFT of task Y - DUR of task Y
It is not a good idea to say "we don't have to start a task until the LST" because you then have no contingency in case anything unexpected happens to cause a delay halfway through the task.
Example 2 |  |  | 5 | 2 | 7
Task Y
0 | 5 | 5 | 7 | 2 | 9 | If two or more tasks directly follow task X, do the same calculation for each route.
Task X
2 | 2 | 7 | 5 | 10 | 15 | The LFT of Task X = the earliest of the LSTs of tasks Y and Z.
Task Z
|  |  | 15 | 10 | 25