## Data Entry
PROCESS FAILURE MODE AND EFFECTS ANALYSIS
Item: | Torch |  |  |  | Responsibility: | [5 empty] | FMEA number: | 1
Model: | Red Torch |  |  |  | Prepared by: |  | D.Thomas |  |  |  | Page : | 1
Core Team: | Torch aseemblers ltd. | [9 empty] | FMEA Date (Orig): | 2020-02-14 | Rev: |  | 1
Process Function | Potential Failure Mode | Potential Effect(s) of Failure | Sev | Class | Potential Cause(s)/ Mechanism(s) of Failure | Occur | Current Process Controls | Detec | RPN | Recommended Action(s) | Responsibility and Target Completion Date | Action Results
[12 empty] | Actions Taken | Sev | Occ | Det | RPN
Obtain materials | No parts available | Unable to build assembly | 10 |  | Supplier failed to deliver | 5 | No controls | 10 | 500 | Inventory control | Stores ASAP | Supplier quality review | 2 | 2 | 3 | 12
Assembly | Housing body threads cross threaded | Unable to assemble torch | 8 |  | Poor assembly screwing parts tegether | 6 | No controls | 2 | 96 | Awareness training | Build Technician | Review SOP and update | 2 | 2 | 3 | 12
| LED's in head missing | Unable to emit light | 8 |  | Poor quality from supplier | 5 | No controls | 8 | 320 | Internal quality control | QMS | Review QMS and update | 2 | 2 | 3 | 12
| No springs in battery cartridge | Unable to securely store batteries | 8 |  | Poor quality from supplier | 5 | No controls | 2 | 80 | Internal quality control | QMS | Review QMS and update | 2 | 2 | 3 | 12
| Switch lid missing 'O' ring | Unable to seal unit | 8 |  | Poor assembly when building 'O' ring to part | 6 | No controls | 10 | 480 | Awareness training | Build Technician | Review SOP and update | 2 | 2 | 3 | 12
| Switch lid missing spring | Unable to complete circuit with cartidge | 8 |  | Poor quality from supplier | 5 | No controls | 5 | 200 | Internal quality control | QMS | Review QMS and update | 2 | 2 | 3 | 12
| Switch lid thread damaged | Unable to encase battery cartidge | 8 |  | Poor assembly screwing parts tegether | 6 | No controls | 2 | 96 | Awareness training | Build Technician | Review SOP and update | 2 | 2 | 3 | 12
| No batteries | Unable to power torch | 8 |  | Supplier delivery failure | 5 | No controls | 10 | 400 | Inventory control | Stores ASAP | Supplier quality review | 2 | 2 | 3 | 12
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0

## About This Template
This template was written for the American Society for Quality by
Stat Aids
Your feedback is welcome and encouraged. Please e-mail to:
Stat_Aids@yahoo.com