## Sheet1
TASK | DURATION | START DATE | FINISH DATE | PREDECESSORS | COST
Site Set Up | 11 days | Wed 06/05/20 | Wed 20/05/20 |  | 10000
Build Site Area | 3 days | Wed 06/05/20 | Fri 08/05/20 |  | 3000
Install Temporary Services | 2 days | Wed 06/05/20 | Thu 07/05/20 |  | 4000
Build Temporay Roads | 6 days | Mon 11/05/20 | Mon 18/05/20 | 2 | 3000
Substucture | 48 days | Mon 04/05/20 | Wed 08/07/20 |  | 197000
Excavation & Pilling | 14 days | Mon 04/05/20 | Thu 21/05/20 |  | 78000
Excavation Formworkss | 12 days | Fri 22/05/20 | Mon 08/06/20 | 6 | 31000
Reinforcment | 8 days | Tue 09/06/20 | Thu 18/06/20 | 7 | 26000
Concrete Pouring | 2 days | Fri 19/06/20 | Mon 22/06/20 | 8 | 36000
Concrete Curing & Strike Formwork | 12 days | Tue 23/06/20 | Wed 08/07/20 | 9 | 26000
Superstructure | 110 days | Thu 09/07/20 | Wed 09/12/20 |  | 201000
Building Frame (Concrete Columns and Beams | 50 days | Thu 09/07/20 | Wed 16/09/20 | 10 | 136800
Concrete Curing & Strike Formwork | 15 days | Thu 17/09/20 | Wed 07/10/20 | 12 | 20000
External Brickwork | 45 days | Thu 08/10/20 | Wed 09/12/20 | 13 | 45000
Steel Framed Roof | 52 days | Mon 12/10/20 | Tue 22/12/20 |  | 173000
Constrct Steel Frame | 12 days | Mon 12/10/20 | Tue 27/10/20 | 13 | 112000
Finishes to the Roof | 40 days | Wed 28/10/20 | Tue 22/12/20 | 16 | 61000
Scaffolding | 4 days | Thu 08/10/20 | Tue 13/10/20 |  | 40000
Construct Scaffolding | 2 days | Thu 08/10/20 | Fri 09/10/20 | 13 | 30000
Strike Scaffolding | 2 days | Mon 12/10/20 | Tue 13/10/20 | 19 | 10000
Internal Works | 97 days | Wed 23/12/20 | Thu 06/05/21 | 17 | 423000
Internal Stucture | 30 days | Wed 23/12/20 | Tue 02/02/21 | 17 | 24000
Doors | 3 days | Wed 03/02/21 | Fri 05/02/21 | 22 | 21000
Skirting Boards | 3 days | Mon 08/02/21 | Wed 10/02/21 | 23 | 18000
Floor | 24 days | Thu 11/02/21 | Tue 16/03/21 | 24 | 310000
Screeding | 4 days | Wed 17/03/21 | Mon 22/03/21 | 25 | 23000
Plastering | 33 days | Tue 23/03/21 | Thu 06/05/21 | 26 | 27000
Servicing | 22 days | Wed 03/02/21 | Thu 04/03/21 |  | 240000
Eletrical | 20 days | Wed 03/02/21 | Tue 02/03/21 | 22 | 140000
Mechanical | 22 days | Wed 03/02/21 | Thu 04/03/21 | 22 | 100000
Internal Finishes | 55 days | Fri 07/05/21 | Thu 22/07/21 |  | 169000
Carpentry | 20 days | Fri 07/05/21 | Thu 03/06/21 | 27 | 30000
Painting | 20 days | Fri 04/06/21 | Thu 01/07/21 | 32 | 21000
Floor Finishes | 15 days | Fri 02/07/21 | Thu 22/07/21 | 33 | 64000
Ceiling Finishes | 15 days | Fri 04/06/21 | Thu 24/06/21 | 32 | 51000
Clean Up | 5 days | Fri 25/06/21 | Thu 01/07/21 | 35 | 3000
External Works | 153 days | Fri 22/05/20 | Tue 22/12/20 |  | 61000
Drainage | 64 days | Fri 22/05/20 | Wed 19/08/20 | 6 | 51000
Landscaping | 50 days | Wed 14/10/20 | Tue 22/12/20 | 20 | 10000
|  |  |  | Total Cost | 1474000