LV6 Contemporary Themes

– Conference Learning Log

For: module:M6X01931 Dale Clarke

| Student Name: | Erol Asan 1814997 |
| --- | --- |

| Week 1 | Monday July 20th, 2020 |
| --- | --- |
| Planning: - It was determined that the event name will to be ‘’Hospitality Opportunities 2020’’ - We split the requirements into 4 so each person can be in charge of a major department.. - A meeting will be set for each week, Monday with ulterior minor meetings to be set up if situations require so.. - We set up the planning schedule for the period of time leading to the event. - The final venue was determined as : The Leonard Hotel, London, represented by Victor Ivanov (main contact person) - The date of the event was set. (05.09.2020) |  |
| Organising: - We have divided the duties and responsibilities: - Team Selection: Marketing and Advertising: Narcisa Event manager and guest speaker responsable: Andreea Venue liaison and guest services. Mihaela Technical and event coordinator Erol |  |
| Managing: - A schedule has been created for the project. - Group chats and group access Documents have been created - Minutes will be taken by the management through the project. - Management team to offer support through the project. |  |
| Marketing: - To define a marketing campaign.. - To communicate with the rest of the team. - Innovate and design any marketing material for the conference |  |
| Technical: - Assisting in improving standards at the venue - Received list of assets at the venue. Created a list of project needs for the event - Received available staff list with job descriptions - I am in charge of the set-up of the initial recommendations for event staging. - Venue facilities lists received. - Fire codes and legal prerequisites to be discussed on location on a later date. |  |
| Problems/Resolution Action Plan: - As a first team meeting the issues have been discussed and the point persons have been briefed on potential issues to look for. - Being in the first stage, contract issues have been a major concern. - The venue has presented various complications and limitations. The details will be discussed at a later date when the file has been created.. - It has been decided that whenever a problem arises , it will be presented forward to the team discussion. - The team has to keep in touch with each other as well as with the support staff and outside vendors . |  |
| Focus for the Week: - Creative thinking on how to deliver the event in the most successful way. - Job Fair to be arranged, details needed. - Teams to be allocated at the event site. - Theme to be discussed - Schedules to be set. - Contracts to be approved and signed. |  |

Student Signature: Erol Asan Date: 24-07-2020

| Week 2 | Monday July 27th, 2020 |
| --- | --- |
| Planning: - Initial budget specifications outlined. Detail to follow when more relevant numbers are known. - Contract specifications have been analysed and signed.(Andreea). - Job fair available position descriptions received from partnering hotels. (Emma). - Initial Discussions with Keynote speakers on setting speech themes. - Highlighting individual chosen themes & allocating general conference decorations accordingly. |  |
| Organising: - Theme chosen: Hotel Industry Job Market in 2020 · Individual themes specified: - Narcisa :Welcoming speech/ Initial presentation of what is to come - Emma: Motivational speech on finding a job in the current job market. - Erol:Question and Answer - Andreea: Closing speech. Discussion on context, presentation scheduling and initial readiness · Guest speaker arranged: - Rajesh Agrawal, deputy mayor of London - Muhammad Cassamo, UWTSD Placement Coordinator - Dale Clarke, UWTSD Lecturer |  |
| Managing: - · Meeting between partners successful in setting a requirement list for the following week. - · Project managers have shown efficiency in dealing with issues in teams. - Marketing Manager Narcisa, has asked all team members for additional materials to aid her in structuring the marketing campaign. I have supplied her with materials gathered on the location. |  |
| Marketing: - Marketing Manager Narcisa, has asked all team members for additional materials to aid her in structuring the marketing campaign. - Marketing supervisor Narcisa set up an auxiliary team support for the marketing plan and future endeavours concerning my departments. - The required materials have been discussed, that need online marketing, campaign, presence on all major social platforms( FB, Instagram ,LinkedIn, Twitter), the necessity of approaching an outside company for the creation and print-outs for event pamphlets. |  |
| Technical: - An outside company has been contracted in order to aid with information handling , social media campaign and website support. - Website template approved for build, more information is required for the site from all other department heads, I requested more meetings with the marketing team to help set up for the event. - Logs have been updated on progress in the previous week - Logo design suggestion approved by the managing team. - On site walkthrough scheduled for next week, 2 days before team meeting, to examine the site structure, staging and organization on preparation up for the event. |  |
| Problems/Resolution Action Plan : - All team members must keep in contact to avoid problems from the previous week, lack of communication registered and fixed by IT - Meetings must be kept on schedule and in future team leaders must be in touch with each other all throughout the various stages. - Lack of understating roles and responsibilities handled by Andreea (team leader) - Competition between department heads encouraged, to get more ideas on the discussion table - A debate sistem has been created so team members can present their pitches for all to determine to be usable if they do not have any have issues. |  |
| Focus for the Week: - I am to meet with Narcisa to set up for marketing and create event publicity videos. - Narcisa has agreed to have the event marketing plan totally set up and the first stage of online advertising to go out publicly. - Auxiliary team meetings to be set for planning different aspects of organisation. - Next stage of publicity to be set up and sponsors to show prominently. - Creating an Email group to be prepared for information exchange with outside contractors, sponsors, advertisers, and venue owners as more information is exchanged. |  |

Student Signature: Erol Asan__________________________________ Date: 29/07/2020 _________________________________

| Week 3 | Monday August 3rd, 2020 |
| --- | --- |
| Planning: - Recording of promo videos for advertisement, with help from the venue, guest speakers and support staff - Social media campagne to to show how current we are with the needs of those in the project scope. - Final approval by Andreea for the legal contracts and signatures collected. - All supporting documents to be sent to me for upload on website - All team members to submit final pitches for any additional event requirements.Event should be finalized by next week (all major areas of interest) - Pictures are all set and sent to the technical team to be uploaded. - On site meeting between Mihaela and the Food and Beverage Manager of the venue scheduled with my help. The final menu approved. |  |
| Organising: - Subgroups set up for exchange of ideas. - I helped set up a professional team (outside contractors) for promotional video recording as well as for the event video log creation. - Narcisa(Marketing) and I finalized all pamphlet designs and additional boards for promotional purpose as well as the information share structure for each individual booth of the participating sponsors (Hotel Managers) - Team Leader Andreea to do spot checks with individuals to revise and verify progress and correct any potential issues in my areas of control. - This week is the deadline for extra marketing information that must be in the pamphlets. |  |
| Managing: - Managing team approved the Slogan ‘’New opportunities , from Here.’’ - Deadline set for all promotional materials as 1st August, after that date no further changes can be made, print process must start. - Marketing goals set and meetings to be set up between Narcisa and each of the sponsors for final presentation and approval of materials for upload by my team to the site.. |  |
| Marketing: - Marketing (Narcisa) to work with Technical (Me) for site promotional ideas, further meetings to take place at the venue from now on to visualize projected plans on location. - Final meetings between Marketing and Myself before Print Approval for pamphlets and posters - Setting up a ADvertising campaign at local Universities with the help of the guest speakers , UWTSD collaboration needed. |  |
| Technical: - Promotional video uploaded on the website. - Event profile Uploaded to website - All external social media successfully linked to main event website (youtube, LinkedIn, Instagram, Facebook, Twitter etc) - First stage of paid advertising set up on websites, Sponsors have gratuity but other companies need to pay to get their profiles promoted. |  |
| Problems/Resolution Action Plan: - More communication between Mihaela and Andreea as well as Myself and Andreea, no excuses on missing deadlines. |  |
| Focus for the Week: - Promotional access given to sponsors, for next week they have been asked to prepare their own profiles and supporting videos that they want on the website. - Weekly checklist to be set up from now, - Additional materials to be sent to Technical team upon approval from marketing and team leader for direct upload to the official site - Deadline for the site going online is by next week's meeting. |  |

Student Signature: Erol Asan __________________________________ Date: 05/08/2020 _________________________________

| Week 4 | Monday August 10th, 2020 |
| --- | --- |
| Planning: - All deadlines have been set, and all team members are aware of them - General recap and updates on the state of the various secondary tasks linked to the event. - Venue visits to be suggested by team members to verify location staging. |  |
| Organising: - Meetings to be set up between departments to verify progress and further needs - Final Advertiser deadline and Marketing deadline close, so final touches made for pamphlet design, billboards and posters. - A meeting between technical and marketing was scheduled for any support. - Everyone is working towards the deadlines. |  |
| Managing: - Managing team cough up via secondary meetings as a main team meeting not required (all departments are instructed, of given assignments |  |
| Marketing: - Marketing (Narcisa) is waiting for final approval for the marketing plan by the team. - Marketing information has been shared with the team. - Decisions have been made on the layout of the website. |  |
| Technical: - Website Final form ready for launch. Andreea to approve final form. - Site planning and stage setup discussed, Booths have been received from partner hotels and have been verified and placed in storage for the event. They also contain information on job availabilities as well as pre discussed and approved advertising. - Copyright verification stage, I need to meet with a consultant on various trademark, and copyright issues for both the site as well as for the staging of advertiser logos. Require approval from Team Leader (Andreea) before proceeding forward. |  |
| Problems/Resolution Action Plan: - Copyright issues to be solved this week, so that the site can go online. Linked with the main site for the consultancy firm ‘’Grapevine.co.uk’’ for public awareness of the organising team. |  |
| Focus for the Week: - Final Overview of the event to be compiled by Andreea, and be presented to partners for final approval. - Each department must have ready a breakdown of the event features as it pertains to organizing. - Upload of additional Info for the Website. - Final Go ahead for Pamphlets, posters and billboards |  |

Student Signature: Erol Asan __________________________________ Date: 13/08/2020 _________________________________

| Week 5 | Monday August 17th, 2020 |
| --- | --- |
| Planning: - Website launched successfully. All advertisers agreed on content.Small changes to be made if necessary in the future week. - Updating contact info for advertisers and media contacts - Team meeting on the event site for final review of the location, and layout as suggested by me as staging director. - Final sign-off of all legal documents and agreements done by team leader (Andreea) - Final menu to be made public by F&B (Emma) on the website. - Maintaining contact with advertisers and others in the marketing team (Narcisa) - To update the flyers with the last added information, Menu, Guest speakers, Advertiser logo . |  |
| Organising: - Organizing an online meeting if required with needed team members to discuss unforeseen problems. - All team members instructed to keep in touch, and respond to emails in a timely manner. - Team call scheduled every day at 3:00 PM to discuss changing events |  |
| Managing: - All goals set, team members instructed on needed assignments - No extra management instructions given. |  |
| Marketing: - Updating advertiser info on site according to their requirements - Promoting the event on social media - Responding to queries from the public - Responding to questions from involved persons |  |
| Technical: - All profiles of the team are ready for upload for publicity purposes. - All sections are filed with adequate information. - Suggestion to add another section for assignments paper to be added on the website. |  |
| Problems/Resolution Action Plan: - No issues reported by any team members, advertisers, promoters, or the host venue in the final stretch before the event is to take place. |  |
| Focus for the Week: - Helping guest speakers with their needs for their presentations (audio/video) - At the venue, final arrangements to be made. - Maintaining the site and updates as the promotional campaign continues on social media, expanding our teams presence and that of the event itself to increase awareness for the target audience. |  |

Student Signature: Erol Asan __________________________________ Date: 19/08/20 _________________________________

| Week 6 – Final Week | Monday August 24th, 2020 |
| --- | --- |
| - All team members reported readiness and all tasks finalized. - No problems. - No more changes to be made. - Social media campaign to be continued by the marketing team.(Narcissa) - All team members on stand-by according to instructions from team leader (Andreea) for any last minute bulletins. - F&B reports all is ready. (Emma) - Site staging Ready according to me as technical manager. Event set to take place according to plan |  |

Student Signature: Erol Asan __________________________________ Date: 27/08/20 _________________________________

| Conference Review | Planning; Organisation; Management; Marketing of the Event and Conference Delivery |
| --- | --- |

While the Job Fair proved to be successful in attracting both employers and potential employees under the same roof, the planning of such an event proved to be difficult under the management of such a small team (4 People). While the initial plans and meetings proved to be all encompassing, subsequent weeks, as issues emerged and deadlines needed to be both set and met, team members saw difficult decisions needed to be made with little to no information, this happened because of the lack off experience that manifested itself through poor prioritization but the issues managed to be resolved by the end of the 6 week term before the event actually took place. All parties involved stated great satisfaction with the team for executing the job fair, overall 200+ people left with interviews, scheduled further meetings with employers, and the partner of this event UWTSD, also had several dozen potential students well convinced that an education is a good way to move forward. We thank all participants for their involvement as well as all vendors, subcontractors, the Venue, sponsors and advertisers. Also we applaud our guest speakers for taking the time to share with us, their wisdom and words of encouragement. We welcome any future collaboration with UWTSD and our other partners.

# Appendixes:

Location: Online – Microsoft Teams
Date: 20/04/20
Time:	9am – 12pm