Establishment of a New Precision Manufacturing Facility for Sterling Precision Engineering Plc’s Joint Venture with Donghai Industrial Group

A project plan prepared in the role of Project Manager, covering project outputs, activities, the Work Breakdown Structure, delivery milestones and resource requirements.

Module: Project Management (LCBB6006)

Lecturer: Zainab Atta

Prepared by: Kremena Petrova Nedelcheva

Student Number: 2336425

Role: Project Manager, Sterling Precision Engineering plc

Date: 4 July 2026

# Table of Contents

Table of Contents	2

1. Introduction	3

2. Aim, Objectives and Scope	4

2.1 Aim	4

2.2 Objectives	4

2.3 Scope	4

3. Project Delivery Plan	6

3.1 Project Outputs	6

3.2 Activities Required to Deliver the Outputs	6

3.3 Work Breakdown Structure (WBS)	7

3.4 Deliverables, Milestones and Timeline	9

3.5 Resource Requirements (Personnel and Material)	10

4. Conclusion	11

5. Reference List	12

Right-click the contents above and choose "Update Field" in Word to populate page numbers.

# 1. Introduction

Sterling Precision Engineering plc is a UK-based manufacturer of precision-machined components for the automotive and industrial equipment sectors, headquartered in the West Midlands. the company has agreed a strategic joint venture with Donghai Industrial Group, a Chinese precision manufacturer based in Jiangsu Province, to establish a co-owned production facility in the UK. The venture allows Sterling to access Donghai's manufacturing capacity and component technology, while giving Donghai a manufacturing and distribution base inside the UK and European market.

A project, as defined by the Project Management Institute (2021), is a temporary endeavour undertaken to create a unique product, service, or result, and this initiative meets that definition precisely: it has a clear start and end date, a defined budget, and a one-off deliverable - a fully operational manufacturing facility - rather than an ongoing operational function. This document sets out the project plan for delivering that facility, written from the perspective of the Project Manager.

The project involves leasing and fitting out an existing 4,500 m² industrial unit in Coventry, installing a new precision machining line (part sourced from Donghai's existing supply chain in China), integrating shared digital systems between the two partner organisations, recruiting and training a joint workforce, and achieving the quality and safety certifications needed to begin commercial production. The plan follows recognised project management practice to define the project's scope, deliverables, schedule and resources.

# 2. Aim, Objectives and Scope

## 2.1 Aim

The aim of this project is to establish a fully operational, quality-certified precision manufacturing facility in the UK within 12 months, capable of supplying both Sterling Precision Engineering plc and Donghai Industrial Group's shared customer base from an agreed capital budget of £9.2 million.

## 2.2 Objectives

the following objectives have been set:

- Secure and fit out a leasehold industrial facility of at least 4,500 m² in the West Midlands within 5 months of project start.

- Procure, install and calibrate the full precision machining line, combining UK-sourced and Donghai-supplied equipment, within 7 months of project start.

- Design and implement shared digital and ERP systems linking Sterling's and Donghai's operations within 8 months of project start.

- Recruit and train a workforce of 45 production, quality and support staff, including cross-cultural working practices for the joint UK–China management team, within 9 months of project start.

- Achieve ISO 9001 and IATF 16949 quality certification prior to commercial production start-up.

- Complete a successful pilot production run and hand over an operational facility to the joint venture board within 12 months and within the approved £9.2 million budget.

## 2.3 Scope

The scope follows the Work Breakdown Structure (PMI, 2019); work outside the WBS is excluded.

In scope:

- Leasing and fitting out the Coventry production facility, including civil, mechanical and electrical works.

- Procurement, import, installation and calibration of production machinery.

- Design and implementation of shared IT and ERP systems between the two partner organisations.

- Recruitment, technical training and cross-cultural team training for the initial operating workforce.

- Achievement of quality, health and safety, and environmental certifications required for production start-up.

- Pilot production run, commissioning and formal handover to the joint venture's operations team.

Out of scope:

- Ongoing commercial production once the facility has been handed over (this becomes a JV operational responsibility, not a project activity).

- Construction of a new-build facility - the project uses an existing industrial shell rather than ground-up construction.

- Sales, marketing and customer contract negotiation for the facility's output.

- Any capital works at Donghai's existing Chinese facilities.

# 3. Project Delivery Plan

This section sets out the project's outputs, the activities required to deliver them, the Work Breakdown Structure, the delivery timeline and milestones, and the resourcing required to complete each area of work.

## 3.1 Project Outputs

The table below lists the direct outputs (deliverables) of this project, along with the outcome each is intended to enable.

| Project Output (Deliverable) | Direct Result / Outcome Enabled |
| --- | --- |
| Leased and fitted-out 4,500 m² production facility | Provides the physical space and services needed for manufacturing operations |
| Installed and calibrated precision machining line | Enables production of components to the specification agreed with Donghai |
| Integrated ERP and digital systems linking Sterling and Donghai | Allows shared visibility of orders, inventory and production data across both partners |
| Trained and certified workforce (45 staff) | Provides the operational capability to run the facility safely and to specification |
| ISO 9001 / IATF 16949 certification | Enables the facility to supply automotive-sector customers under both partners' quality frameworks |
| Health & safety and environmental compliance sign-off | Provides legal authority to operate the site and protects the workforce |
| Successful pilot production run and commissioning report | Demonstrates the facility is capable of meeting output and quality targets before full handover |
| Project closure report and lessons-learned log | Provides the joint venture board with a record for future capital projects |

## 3.2 Activities Required to Deliver the Outputs

Each output is grouped into seven work packages. These seven work packages form the top level of the Work Breakdown Structure developed in Section 3.3.

1.0 Project Management & Governance

Establishing the project charter, governance structure, planning, monitoring and closure activities that run throughout the project.

2.0 Site Acquisition & Facility Fit-Out

Selecting, leasing and physically preparing the Coventry site, including design, planning permission and construction works.

3.0 Production Equipment Procurement & Installation

Specifying, purchasing, importing, installing and calibrating the machining line.

4.0 Digital Systems & ERP Integration

Designing and implementing the IT infrastructure and ERP interface linking the two partner organisations.

5.0 Workforce Recruitment, Training & Certification

Recruiting, training and certifying the operating workforce, including cross-cultural team working.

6.0 Quality, Health & Safety and Regulatory Compliance

Building the quality management system and achieving the certifications and compliance sign-offs required to operate.

7.0 Testing, Commissioning & Handover

Running a pilot production batch, resolving defects, and formally handing the facility to operations.

## 3.3 Work Breakdown Structure (WBS)

The WBS breaks each work package into activities for scheduling, costing and resource allocation (PMI, 2019; Lock, 2013).

1.0  Project Management & Governance

1.1  Project Initiation

1.1.1 Develop project charter and business case

1.1.2 Confirm joint venture governance structure with Donghai Industrial Group

1.2  Planning

1.2.1 Develop project management plan (scope, schedule, cost, risk)

1.2.2 Develop stakeholder and bilingual communication plan

1.3  Monitoring & Control

1.3.1 Weekly progress reporting and RAID log management

1.3.2 Monthly joint venture steering board review

1.4  Closure

1.4.1 Post-implementation review

1.4.2 Lessons learned and handover to operations

2.0  Site Acquisition & Facility Fit-Out

2.1  Site Selection

2.1.1 Site survey and shortlist of West Midlands units

2.1.2 Lease negotiation and signature

2.2  Design

2.2.1 Facility layout design (production, warehouse, office)

2.2.2 Planning permission and building control submission

2.3  Construction & Fit-Out

2.3.1 Civil and structural works (flooring, services)

2.3.2 Mechanical and electrical (M&E) installation

2.3.3 Production area fit-out

3.0  Production Equipment Procurement & Installation

3.1  Procurement

3.1.1 Equipment specification aligned with Donghai's standards

3.1.2 Supplier tendering and purchase orders (UK and China)

3.2  Logistics

3.2.1 Import and customs clearance for China-sourced machinery

3.2.2 Delivery and positioning on site

3.3  Installation & Calibration

3.3.1 Machine installation

3.3.2 Calibration and test runs

4.0  Digital Systems & ERP Integration

4.1  Systems Design

4.1.1 IT infrastructure design (network, servers, security)

4.1.2 ERP interface design linking Sterling and Donghai systems

4.2  Implementation

4.2.1 Hardware installation

4.2.2 ERP configuration and data migration

4.3  Testing

4.3.1 System integration testing

4.3.2 User acceptance testing

5.0  Workforce Recruitment, Training & Certification

5.1  Recruitment

5.1.1 Define roles and job descriptions

5.1.2 Recruitment campaign and selection

5.2  Training

5.2.1 Technical and machine operation training

5.2.2 Cross-cultural and communication training for joint teams

5.3  Certification

5.3.1 Health and safety certification (IOSH/NEBOSH)

5.3.2 Role-specific competency sign-off

6.0  Quality, Health & Safety and Regulatory Compliance

6.1  Quality Management

6.1.1 ISO 9001 / IATF 16949 gap analysis

6.1.2 Quality management system documentation

6.2  Health & Safety

6.2.1 Risk assessments and method statements

6.2.2 Fire, environmental and COSHH compliance

6.3  Certification Audit

6.3.1 External certification audit

6.3.2 Corrective actions close-out

7.0  Testing, Commissioning & Handover

7.1  Trial Production

7.1.1 Pilot batch production run

7.1.2 Quality validation of pilot output

7.2  Commissioning

7.2.1 Snagging and defect resolution

7.2.2 Operational readiness review

7.3  Handover

7.3.1 Handover to operations and JV board sign-off

7.3.2 Project closure report

The WBS above provides the basis for the schedule, milestones and resource assignments set out in the remaining sections.

## 3.4 Deliverables, Milestones and Timeline

The project runs for 12 months (August 2026–July 2027), with activities sequenced according to logical dependencies. The table below shows the timing of each work package, its key deliverable, and the milestone used to confirm it is complete.

| WBS | Work Package | Duration (Months) | Key Deliverable | Milestone |
| --- | --- | --- | --- | --- |
| 1.0 | Project Management & Governance | 1–12 (ongoing) | Governance framework, reporting cadence, closure report | M1: Charter and governance signed off (Month 1) |
| 2.0 | Site Acquisition & Facility Fit-Out | 1–5 | Leased, designed and fitted-out facility shell | M2: Lease signed (Month 2) · M3: Fit-out complete (Month 5) |
| 3.0 | Equipment Procurement & Installation | 3–7 | Installed and calibrated machining line | M4: Equipment installed and calibrated (Month 7) |
| 4.0 | Digital Systems & ERP Integration | 4–8 | Live, integrated ERP and IT systems | M5: Systems go-live (Month 8) |
| 5.0 | Workforce Recruitment, Training & Certification | 5–9 | Trained, certified workforce of 45 staff | M6: Workforce trained and certified (Month 9) |
| 6.0 | Quality, Health & Safety and Compliance | 2–9 | ISO 9001 / IATF 16949 certification | M7: Certification achieved (Month 9) |
| 7.0 | Testing, Commissioning & Handover | 9–12 | Commissioned facility, pilot run report | M8: Pilot run successful (Month 11) · M9: Facility handover (Month 12) |

Milestones M2 through M9 form the critical sequence of the project: a delay to the lease signature (M2) or equipment installation (M4) has a direct knock-on effect on training (M6) and the pilot run (M8), since staff cannot be trained on machinery that is not yet installed, and production cannot be trialled before the workforce is certified.

## 3.5 Resource Requirements (Personnel and Material)

Resources are assigned to each work package to support effective planning and control (Maylor and Turner, 2022).

| Work Package | Key Personnel | Key Material / Equipment Resources |
| --- | --- | --- |
| 1.0 Project Management & Governance | Project Manager; PMO Coordinator; JV Steering Board (Sterling and Donghai directors); bilingual liaison/interpreter | Project management software (e.g. MS Project); reporting templates; video-conferencing facilities for the China-based partner |
| 2.0 Site Acquisition & Facility Fit-Out | Site/Construction Manager; architect; planning consultant; M&E contractor | Leasehold industrial unit; construction materials; mechanical and electrical equipment; fit-out materials |
| 3.0 Equipment Procurement & Installation | Procurement Lead; mechanical engineers; logistics/customs coordinator; installation technicians (including Donghai-supplied specialists) | Precision machining equipment; calibration tools; freight and import logistics; spare-parts inventory |
| 4.0 Digital Systems & ERP Integration | IT Infrastructure Lead; ERP consultant; network engineer; data migration specialist | Servers and network hardware; ERP software licences; cybersecurity software |
| 5.0 Workforce Recruitment, Training & Certification | HR/Recruitment Manager; Training Coordinator; Donghai technical trainers; Health & Safety Officer | Bilingual training manuals; e-learning platform; personal protective equipment (PPE) |
| 6.0 Quality, Health & Safety and Compliance | Quality Manager; Health & Safety Advisor; external ISO/IATF auditor | Quality management system software; risk assessment templates; certification audit fees |
| 7.0 Testing, Commissioning & Handover | Operations Manager; quality inspectors; JV steering board (sign-off) | Trial raw material stock; testing and measurement equipment; snagging and defect-tracking tools |

The international nature of the project requires bilingual communication and cross-cultural coordination alongside technical expertise.

# 4. Conclusion

This plan outlines the outputs, WBS, schedule and resources needed to deliver the facility within 12 months and the approved £9.2 million budget. Delivered as planned, the facility will give both partner organisations a certified, operational manufacturing base from which to begin commercial production.

# 5. Reference List

Association for Project Management (2019) APM Body of Knowledge. 7th edn. Princes Risborough: Association for Project Management.

Kerzner, H. (2022) Project Management: A Systems Approach to Planning, Scheduling, and Controlling. 13th edn. Hoboken, NJ: Wiley.

Larson, E.W. and Gray, C.F. (2021) Project Management: The Managerial Process. 8th edn. New York: McGraw-Hill Education.

Lock, D. (2013) Project Management. 10th edn. Farnham: Gower.

Maylor, H. and Turner, N. (2022) Project Management. 5th edn. Harlow: Pearson.

Project Management Institute (2019) Practice Standard for Work Breakdown Structures. 3rd edn. Newtown Square, PA: Project Management Institute.

Project Management Institute (2021) A Guide to the Project Management Body of Knowledge (PMBOK Guide) and the Standard for Project Management. 7th edn. Newtown Square, PA: Project Management Institute.