## Copy of Tai Tarian Office Build
Tai Tarian Office Building | Duration | Start | Finish | Per M2 | Project size (m2) | Total estimated costs
Planning and Design | 84d | 2019-07-29 | 2019-11-21
Working drawings | 21d | 2019-09-01 | 2019-09-27
Architectural plans | 65d | 2019-07-29 | 2019-10-25
Structural plans | 6d | 2019-10-28 | 2019-11-04
Mechanical plans | 6d | 2019-11-05 | 2019-11-12
Electrical plans | 6d | 2019-11-13 | 2019-11-20
Planning completed | 2d | 2019-11-20 | 2019-11-21
Bidding | 15d | 2019-11-22 | 2019-12-12
Contract review | 4d | 2019-11-22 | 2019-11-27
Bid evaluation | 5d | 2019-11-28 | 2019-12-04
Organise project start date | 6d | 2019-12-05 | 2019-12-12
Site Preparation | 43d | 2019-12-12 | 2020-02-10
Site access - research | 8d | 2019-12-12 | 2019-12-23
Services available and req. | 10d | 2019-12-23 | 2020-01-03
Layout - site conditions | 2d | 2020-01-06 | 2020-01-07
Resources - local subs | 8d | 2020-01-08 | 2020-01-17
Security measures for site | 3d | 2020-01-20 | 2020-01-22
Materials - source local supply | 13d | 2020-01-23 | 2020-02-10
Site work - below grade | 83d | 2020-02-11 | 2020-06-04
Excavation and land clearing | 11d | 2020-02-11 | 2020-02-25
Initial grading | 11d | 2020-02-25 | 2020-03-10
Final grading | 6d | 2020-03-11 | 2020-03-18
Set foundations | 11d | 2020-03-19 | 2020-04-02
Rough services | 9d | 2020-04-06 | 2020-04-16
Sewer works | 9d | 2020-04-20 | 2020-04-30
GS Heat pump location | 5d | 2020-05-01 | 2020-05-07
Water and filtration | 8d | 2020-05-08 | 2020-05-19
Install conduit | 1d | 2020-05-20 | 2020-05-20
Backfill | 11d | 2020-05-21 | 2020-06-04
Site work - above grade | 34d | 2020-05-13 | 2020-06-29
Erect steel structure | 16d | 2020-05-13 | 2020-06-03
Columns and walls | 16d | 2020-06-08 | 2020-06-29
Framing and fitting out - Part 1 | 63d | 2020-06-30 | 2020-09-24
External doors | 6d | 2020-06-30 | 2020-07-07
Windows | 6d | 2020-07-08 | 2020-07-15
Floors | 11d | 2020-07-15 | 2020-07-29
Internal walls | 11d | 2020-07-30 | 2020-08-13
Electrical 1st fix | 10d | 2020-08-17 | 2020-08-28
Plumbing installation 1st fix | 11d | 2020-08-31 | 2020-09-14
Suspended ceiling tiles | 6d | 2020-09-13 | 2020-09-18
Floor finishes | 6d | 2020-09-17 | 2020-09-24
Fitting out - Part 2 | 26d | 2020-09-25 | 2020-10-31
Electrical 2nd fix | 6d | 2020-09-25 | 2020-10-02
Plumbing 2nd fix | 6d | 2020-09-25 | 2020-10-02
Fixtures and fittings | 11d | 2020-09-25 | 2020-10-09
Decoration | 16d | 2020-10-09 | 2020-10-30
Project finish date | 1d | 2020-10-31 | 2020-10-31
Plant
180 degree backhoe loader
360 degree excavator
Loading shovel
Overhead Gantry Crane
Lorry Loader
Forward Tipping dumper
Ride on roller
Breaker
Cherry picker
Bulldozer
Wheel barrow
Personel
Directors
Project board
Employee management
Project Manger
Consultant
Lead designer
Design Team
Architect
Services engineer
Structural engineer
Specialist designer
CDM Co-ordinator
Contractor
Sub-Contractors
Suppliers
Basic materials
Steel frame system
I-beams and columns
Rebar
Steel joists, framing
Purlic and cladding rolls
Concrete
Building insulation
Building envelope
Weatherproof systems
Ground source heat pump
Rainwater harvesting system
Internals:
Carpentry
Doors, hardware
Electrical services
Plumbing services
Surface finishing
Fire alarm system
Finishes
HVAC (Heating, ventilation and AC)
Costings
These costings are based on the average build of a Buisness Park construction from the Spons 2016 edition (costs per m2)
Substructure |  |  |  | 71.88 | 2043 | 146850.84
Frames, Uppers floors and stairs |  |  |  | 130.39 | 2043 | 266386.77
Roof |  |  |  | 105.9 | 2043 | 216353.7
External wall, windows and doors |  |  |  | 139.45 | 2043 | 284896.35
Internal walls and Partitions and doors |  |  |  | 53.94 | 2043 | 110199.42
Wall finishes |  |  |  | 11.2 | 2043 | 22881.6
Floor finishes |  |  |  | 13.05 | 2043 | 26661.15
Ceiling finishes |  |  |  | 8.69 | 2043 | 17753.67
Furniture and fittings |  |  |  | 6.29 | 2043 | 12850.47
Sanitary appliances |  |  |  | 4.21 | 2043 | 8601.03
Disposal Installations |  |  |  | 5.42 | 2043 | 11073.06
Water installations |  |  |  | 0.55 | 2043 | 1123.65
Space heating, AC and ventilation |  |  |  | 65.91 | 2043 | 134654.13
Electrical and Gas installations |  |  |  | 46.79 | 2043 | 95591.97
Incoming services |  |  |  | 1.66 | 2043 | 3391.38
Protective Installations |  |  |  | 1.41 | 2043 | 2880.63
Communication Installations |  |  |  | 6.21 | 2043 | 12687.03
Specialists Installations |  |  |  | 15.63 | 2043 | 31932.09
Builders work in connection |  |  |  | 1.66 | 2043 | 3391.38
Preliminaries and Contingency |  |  |  | 141.49 | 2043 | 289064.07
1699224.39
Costs to be considered:
Car park construction
Design Team
Construction site team
Local Authority fees
Work permits