## Slide 1: Research Methods
3: Project Planning

## Slide 2: Getting organised
It is possible to successfully complete a project without proper planning, but it will be much harder and far more stressful
Planning and setting up a project in advance saves a lot of time and effort in the long term
Not everything needs to be done on a computer
  Use the most efficient mechanism, not the most technologically impressive
Keep backups of paper as well as electronic materials

## Slide 3: Filing system sections
Background documents
Project start-up documents
Project plans
Literature search results
System development documents & models
Fact-finding results
Project control documents
Correspondence
Draft reports
Project handbook
Meeting agendas and minutes

## Slide 4: Your project notebook
This should be relatively informal, and contain things such as
  A diary with brief notes on what you have done each day
  A to-do list (regularly updated!)
  Questions for your supervisor and follow-up actions for yourself
  Ideas on how to solve problems or address requirements
  Notes on newly-identified issues or risks
  Useful bits of information such as websites or software tools that you come across
Notes: Ch5, p108 (Weaver, Success In Your Project)

## Slide 5: Project planning
Always plan a project; don’t just start doing things
Whenever you start something you need to know
  Why are you doing it?
  What is the planned outcome?
  How long it will take?
  What you will do once you’ve finished?
Your project will almost certainly not go according to plan, but a good plan can adapt to change
Plans therefore need to be monitored carefully and (sometimes) adjusted as needed

## Slide 6: The project plan
You plan should attempt to do the following:
  Ensure you can complete all necessary activities in time
  Establish what you need to do each day
  Identify when you need to obtain certain skills
  Identify project dependencies and conflicts
  Demonstrate you your markers that you have thought out the project carefully
  Enable you to track progress
  Identify when you need to have access to particular resources
Notes: Ch5, p109 (Weaver, Success In Your Project)

## Slide 7: Producing a task list
To produce an effective plan you need to identify a set of small tasks you can schedule
A task is something that cannot be meaningfully broken down further but is small enough to estimated accurately
This will normally be between 2 and 15 hours (most are between 4 and 10)
  Anything smaller than this is too detailed
  Anything larger than this will be difficult to estimate effectively
  Larger tasks will also contain smaller tasks that should themselves be scheduled

## Slide 8: Producing a task list
The first step is to create a work breakdown structure
This starts with a list of the high-level phases of the subject
Some of the phases identified will probably resemble the objectives defined in the project proposal
Not all phases will be equal in size
  They don’t need to be, but make sure that everything is covered

## Slide 9: Producing a task list
Phase-level work breakdown structure
0: Smart Home Simulation
1: Literature review
2: Capture req’ments
3: Design simulation
4: Perform tests
5: Critical evaluation
6: Write final report

## Slide 10: Producing a task list
Next, split each phase into the activities involved in that phase to produce a second-level work breakdown structure
3: Design simulation
3.1: Identify building configuration
3.2: Specify smart devices to be included
3.3: Assign devices to building rooms
3.4: Identify operating conditions
3.5 Write appropriate simulation scripts
3.6: Document the design and scripts

## Slide 11: Producing a task list
At this point some of the tasks are still likely to be too big to estimate effectively
  Some tasks may take weeks
  These tasks will need to be split further
3.3: Assign devices to building rooms
3.3.1: Position sensors
3.3.2 Position actuators
3.3.3: Position networking elements
3.3.4: Produce architectural plan of home

## Slide 12: Adding timings to tasks
Once the task list is complete you should estimate how many hours each task will take
  Task length – how many hours are needed, e.g. 6 hours
  Task duration – those hours may have to be split over 2 days, so the duration would be 2 days
A 40-credit module requires 400 hours of work
  Approximately 65 6-hour tasks
  Less than 2 pages at one task per line 
Tasks such as fact-finding, prototyping and writing the final report may be open-ended
  Consider timeboxing these tasks

## Slide 13: Identifying task dependencies
Many of the tasks will come in a logical order
  You cannot demonstrate a prototype before building it!
These are often in long chains of tasks that are interdependent on each other, but independent of tasks in a separate chain
  Defining requirements are probably independent of learning Java
These can be shown in a Gantt chart, with each chain shown as a linked set of tasks

## Slide 14: Identifying planning constraints
Constraints need to be considered when planning a project
Obvious constraints are presentation dates and hand-in dates
  These are shown as milestones
Less obvious constraints include the availability of resources
  Access to specific equipment or people
  Holidays
  Other courseworks

## Slide 15: Contingency planning
You will be over-optimistic in what you think you can do in a set period of time 
You should therefore build time into your plan for contingencies
  Task-level: Identify high-risk tasks and allocate them extra time
  Phase-level: Common practice is to add 20% extra time to phases to cope with unexpected events such as sickness
  Alternative plans: Some tasks may have more time-efficient but less desirable alternatives that could be used if the project falls behind. Identify these early

## Slide 16: Scheduling
Use an appropriate software package to create a Gantt chart
Create the task list before setting any timings
Add any milestones and their dates
Identify task and milestone dependencies by linking tasks with arrows
Take each task in turn and add the start date and projected length
Double-check that you will complete all tasks by their respective milestones and that you are not trying to do too many things in parallel

## Slide 17: If it doesn’t fit…
You may need to tweak some of your tasks to make sure that you can complete the project in the time allotted
If it doesn’t fit after this, you must discuss this with your supervisor
  You may have to change your project objectives or otherwise reduce the scope of your project
You must not just cut time off tasks until it fits
  You will just end up falling behind and having to change the scope later in the project or accept that you will complete the project late
  Neither of these is likely to have a happy ending

## Slide 18: Resources
When planning a project you also need to identify the resources that are needed
Resources come in several types
  Hardware (computers, electronics, interface devices)
  Software (Programming IDEs, analysis software, word processing packages)
  Information (data sets, library access)
  Human (researcher, project supervisor, test subjects, technical support, industrial liaison)
Think about when you need these and for how long; it can impact on your project planning

## Slide 19: Coming Soon…
Next workshop: Descriptive statistics