## Lists (hidden)
Cyber & Technology | People & Behaviour | Operational | Physical & Environmental | Financial | Strategic
Cyber Security | Human Error | Process Failure | Physical Security | Financial Fraud | Strategic
Data Privacy | Insider Threat | Supply Chain | Natural Disaster | Budget Overrun | Political / Regulatory
System Failure | Social Engineering | Business Continuity | Environmental | Economic | Third Party / Vendor
Software/Hardware | Reputational | Compliance / Legal | Health & Safety

## Risk Register
Risk Management Register
Scenario: Financial Management System Group: 3
Risk ID | Hazard / Risk Description | Who is at Risk | Category | Sub Category | Likelihood (1–5) | Severity (1–5) | Risk Score (L × S) | Risk Level | Existing Controls | Additional Controls Needed | Responsible Person | Target Date | Residual Likelihood (1–5) | Residual Severity (1–5) | Residual Risk Score | Residual Risk Level | Status
1 | Ransomware infection of central financial database encrypting customer account records. | Customers, Internal Operations | Cyber & Technology | Malware | 3 | 5 | 15 | Critical | Standard antivirus, weekly system backups. | Deploy EDR, implement immutable offline backups, strict network segmentation. | IT Security Manager | 1 | 5 | 5 | 25 | Critical | Active
2 | Targeted spear-phishing campaign compromising administrator credentials. | IT Staff, Customers | Cyber & Technology | Social Engineering | 4 | 4 | 16 | Critical | Spam filters, annual security awareness training. | Mandatory hardware-token MFA for admins, quarterly simulated phishing tests. | CISO | 2 | 4 | 8 | 32 | Critical | Active
3 | Distributed Denial of Service (DDoS) attack overwhelming the online banking portal. | Customers | Operational | Network Security | 4 | 3 | 12 | High | Basic ISP traffic filtering, redundant load balancers. | Implement dedicated Web Application Firewall (WAF) and Cloudflare DDoS protection. | Network Architect | 2 | 2 | 4 | 8 | Medium | Active
4 | SQL injection exploitation in the investment management portal exfiltrating trading data. | High-Net-Worth Clients | Cyber & Technology | App Security | 3 | 5 | 15 | Critical | Manual code reviews prior to major releases | Automated SAST/DAST pipeline, strict parameterized queries enforcement. | Lead Developer | 1 | 5 | 5 | 25 | Critical | In Progress
5 | Malicious insider deliberately exfiltrating customer PII database to an external drive. | Customers | People & Behaviour | Data Privacy | 2 | 5 | 10 | High | Background checks upon hire, standard RBAC. | Deploy Data Loss Prevention (DLP) tools, disable USB ports on local endpoints. | HR & IT Ops | 1 | 4 | 4 | 16 | Critical | Active
6 | Unauthorized access to loan processing systems via a compromised third-party API key. | Loan Applicants | People & Behaviour | Vendor Risk | 3 | 4 | 12 | High | Annual vendor risk assessments, standard API tokens. | IP whitelisting for API access, frequent key rotation policies, API anomaly monitoring. | Integration Lead | 1 | 4 | 4 | 16 | Critical | Active
7 | Misconfigured cloud storage bucket accidentally exposing disaster recovery backups to the public. | All Stakeholders | Cyber & Technology | Configuration | 3 | 5 | 15 | Critical | Manual cloud infrastructure provisioning. | Implement Infrastructure as Code (IaC) with automated compliance scanning (e.g., CSPM). | Cloud Engineer | 1 | 5 | 5 | 25 | Critical | In Progress
8 | Physical theft of an unencrypted employee laptop containing downloaded transaction logs. | Customers | Physical & Environmental | Hardware | 3 | 3 | 9 | Medium | Kensington locks in office, remote wipe capability. | Enforce Full Disk Encryption (BitLocker/FileVault) via MDM on all mobile devices. | IT Support Lead | 2 | 1 | 2 | 2 | Low | Active
9 | Man-in-the-Middle (MitM) session hijacking on the mobile banking app over public Wi-Fi. | Mobile Users | Cyber & Technology | Mobile Security | 4 | 4 | 16 | Critical | App uses standard HTTPS for connections. | Implement certificate pinning in the mobile app, enforce short session timeouts. | Mobile App Dev | 1 | 4 | 4 | 16 | Critical | Active
10 | Complete localized power failure at the primary data center causing transaction downtime. | Bank Operations | Physical & Environmental | Infrastructure | 2 | 4 | 8 | Medium | Primary Uninterruptible Power Supply (UPS) units. | Install redundant diesel generators, establish hot-site failover protocol. | Facilities Manager | 1 | 2 | 2 | 4 | Low | Active
RISK LEVEL LEGEND
Critical (15–25) |  |  |  | Immediate action — stop or redesign activity
High (10–14) |  |  |  | Urgent controls needed — inform senior management
Medium (5–9) |  |  |  | Monitor closely — additional controls required
Low (1–4) |  |  |  | Acceptable — review periodically

## Risk Heatmap
RISK SCORE HEATMAP - Likelihood × Severity
Use this matrix to identify the risk level for any combination of Likelihood and Severity.
SEVERITY →
← LIKELIHOOD |  | 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Catastrophic
| 5 – Almost Certain | 5 Medium | 10 High | 15 Critical | 20 Critical | 25 Critical
| 4 – Likely | 4 Low | 8 Medium | 12 High | 16 Critical | 20 Critical
| 3 – Possible | 3 Low | 6 Medium | 9 Medium | 12 High | 15 Critical
| 2 – Unlikely | 2 Low | 4 Low | 6 Medium | 8 Medium | 10 High
| 1 – Rare | 1 Low | 2 Low | 3 Low | 4 Low | 5 Medium

## Action Tracker
RISK CONTROL ACTION TRACKER
Risk ID | Risk Description | Action Required | Priority | Responsible Person | Start Date | Target Date | Completion Date | Evidence / Notes | Status

## Guidance Notes
HOW TO USE THIS RISK MANAGEMENT WORKBOOK
SHEETS OVERVIEW
| Risk Register | Complete one row per identified hazard. Risk Score and Risk Level are auto-calculated.
| Risk Heatmap | 5×5 colour-coded matrix showing how Likelihood and Severity combine into a risk level.
| Action Tracker | Log all control actions, assign responsibility, and track completion.
| Guidance Notes | This page — definitions and instructions.
LIKELIHOOD SCALE
| 1 – Rare | Could happen but probably never will (once every 5+ years)
| 2 – Unlikely | Not expected but possible (once every 2–5 years)
| 3 – Possible | Could occur at some time (once per year)
| 4 – Likely | Will probably occur in most circumstances (monthly)
| 5 – Almost Certain | Expected to occur in most circumstances (weekly/daily)
SEVERITY SCALE
| 1 – Negligible | No impact; minor inconvenience
| 2 – Minor | Small impact; easily recoverable
| 3 – Moderate | Noticeable impact; some recovery effort needed
| 4 – Major | Significant impact; difficult to recover from
| 5 – Catastrophic | Severe or irreversible impact
RISK LEVEL GUIDE
| Low (1–4) | Monitor and review periodically; standard controls sufficient
| Medium (5–9) | Manage through routine procedures; monitor more frequently
| High (10–14) | Urgent action required; inform responsible person immediately
| Critical (15–25) | Stop or redesign activity until risk is reduced to acceptable level
RISK CATEGORIES
| Cyber & Technology | Cyber Security, Data Privacy, System Failure, Software/Hardware
| People & Behaviour | Human Error, Insider Threat, Social Engineering, Reputational
| Operational | Process Failure, Supply Chain, Business Continuity, Compliance / Legal
| Physical & Environmental | Physical Security, Natural Disaster, Environmental, Health & Safety
| Financial | Financial Fraud, Budget Overrun, Economic
| Strategic | Strategic, Political / Regulatory, Third Party / Vendor
TIPS FOR STUDENTS
| Research first | Identify risks through research before filling in the register
| Be specific | Describe the hazard clearly — avoid vague terms like 'something goes wrong'
| Think about controls | Consider both existing controls and what additional ones are needed
| Residual risk | After controls are applied, re-score Likelihood and Severity to get residual risk
| Hierarchy of controls | Eliminate > Substitute > Engineering > Administrative > PPE