## Front
Jayne Pierson School of Fashion, Art & Design
NRM1 Feasibility Cost Plan
Company: Alpha Designs
Project Reference: 6023
Dated:

## Status
NRM1 Feasibility Cost Plan
Monday 06/02/2023
Document Status
Revision | Date | Status | Prepared by | Checked by | Authorised by
DISCLAIMER
This document and its contents have been prepared and are intended solely for [Ace Capital Projects Ltd] information and use in relation to [Jayne Pierson School of Fashion, Art & Design]
Faithful+Gould assumes no responsibility to any other party in respect of or arising out of or in connection with this document and/or its contents.
COPYRIGHT
The copyright of this document is vested in Faithful+Gould. This document may not be reproduced in whole or in part without their express written permission.

## Information Used
Information Used & Assumptions
1 | Information Used
All measures have been under taken using the software app Quickscale
2 | General Assumptions;
External Works is excluded unless specifically identified within the cost plan.
External wall build up specified by client.
Costs are based upon the information as provided.
We have assumed a project bank account will not be required for this scheme.
We have assumed that the area of works will be decanted for the project. No allowance is made for throughways or dealing with building occupants.
The exact nature of specification for internal doors, screens, folding partitions and finishes is assumed.
All costs are provisional awaiting design development.
All base costs are based on Q42022
3 | General Notes and Exclusions;
All included costs are subject to variation following design development.
A risk allowance of 10% is included for this estimate.
VAT is excluded from the estimate.
Works will be undertaken in a single phase.
Local Authority Fees
Building Regulation fees
Party Wall Awards
Acquisition & associated legal

## Summary Original
Project details: | Jayne Pierson, School of Fashion, Art & Design
Description: | Phase 2 of Port Talbot College
Building Works Estimate
Based on GIFA of: 3041m2 |  |  |  |  | 1575 | Base Est cost £/m2
| Group Element | Element Type | Total | £/m2
| Group element 0 | FACILITATING WORKS - excluded from scope
|  | Preliminaries | 1824600 | 600
|  | Earthworks | 304100 | 100
|  | Temporary Works | 176000 | 57.8757
|  | 278 Works | 75000 | 24.6629
|  | Services | 90000 | 29.5955
|  | Main Building | 4789575 | 1575
0
Works cost estimate (sub total A) |  |  | 7259275 | 2387.1342
| Current TPI | 1.24
| Forecasted 2024 Q1 TPI | 2.22
12996443.9516
| Wales Location Factor | 0.85
11046977.3589
Project Constraints-Provisional sums
Demolition and site clearence |  |  | 100000
Building Serveys |  |  | 50000
Knotweed treatment |  |  | 30000
Land surveys |  |  | 5000
Tower Crane |  |  | 130000
Traffic management |  |  | 23400
External services-overhead cable removal |  |  | 80000
Project design team fees and other development costs (sub total B)
Maintinance Costs
10% of the overall build cost |  |  | 725927.5 | 238.7134
Whole Life Costing TBC
Base cost estimate A + B (sub total C) |  |  | 12191304.8589 | 2625.8476
Group element 13
| Design Contingency | Risk allowance @ 2.5% | 304782.6215 | 193.5128
| Construction Risk | Risk allowance @ 2.5% | 304782.6215 | 193.5128
| Employers Change Risk | Risk allowance @ 2.50% | 304782.6215 | 193.5128
| Other Mis. Risk | Risk allowance @ 2.5% | 304782.6215 | 193.5128
Total Risk allowances (sub total D) |  |  | 1219130.4859 | 774.0511
Total Construction Cost (C + D) |  |  | 13410435.3448 | 8514.5621
Note on G8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: sponds yellow page 79

## NRM1 CP template
Feasibility Cost Plan
NRM 1 phaseologies
| Feasibiliy Cost Plan | Jayne Peirson, School of Fashion, Art and Design
Ref. | Element | Timesing | Quantity |  | Unit | Rate | Sub-Total | Group-Total | Notes
[6 empty] | £ | £ | £
Internal & External Facilities
| Preliminaries |  |  | 3041 | m2 |  |  | 1824600
| to include managment Cost, site establishment, site supervision & Contingency |  |  |  |  | 500 | 1520500
| Earthworks |  |  | 3041 | m3 |  |  | 304100
| excavate and removal of existing soil for disposal |  |  |  |  | 100 | 304100
| Temporary Works |  |  | 88 | wks |  |  | 176000
| Provisional Sum |  |  |  |  | 2000 | 176000
| 278 Works |  |  | 50 | m |  |  | 75000
| Access Road to site |  |  |  |  | 1500 | 75000
| Services |  |  | 200 | m2 |  |  | 90000
| Mains Electrical and Gas Services |  |  |  |  | 300 | 60000
| Water mains & Domestic cold water system |  |  |  |  | 150 | 30000
| Main Building |  |  | 3041 | m2 |  |  | 4789575
| Based on art theartre, does not include, fixtures, furnishings or equipment. |  |  |  |  | 1575 | 4789575
7259275
Maintinance Costs
| 10% of the overall build cost |  |  | 10 | % |  |  | 725927.5
Whole Life Costing
TBC
[7 empty] | Total Cost | 7985202.5
SECTION SUB-TOTAL