## Project Template
Problem Statement and area of Opportunity
Voice of the Customer: "Again, XYZ Manufacturing's product costs are higher than your competitors. This is the reason you weren't competitive with this latest quotation." Y (Product costs too high) = f (Material Costs too high + Process costs too high + Profit margins too high) Y (Process Costs too high) = f (Incorrect product routing + Incorrect assumptions in product routing + Incorrect processes considered + Non-optimised Processes) Y (Incorrect assumptions in product routing)
Business Need and Justification
Of 20 quotations submitted to customers from January 2019 to December 2019, 8 were unsuccessful due to product costs too high. 40% unsuccessful in 12 months. Reduce this to 10%.
Risks and Issues |  |  |  | Assumptions and Dependencies
Project Ownership / Approval
Project Manager | Paul Dombey |  | Project Champion | Florence Dombey |  | Approval Date
Project Number |  |  | Process Owner | John Carker
Financial Benefits / Timing
Financial Benefits |  |  | Estimated Expenses / Investment |  |  | Schedule
| Goal | Actual |  | Goal | Actual |  | Goal | Actual
Incremental Sales | +30% |  | Expenses Incremental to Operating Budget |  |  | Measure | 2020-12-31
Profitability (% OI) | +12% |  |  |  |  | Analyse | 2021-02-01
Payback Period (yrs) |  |  | Capital | Zero |  | Improve | 2021-03-15
Annual Savings | £180k |  | Other; 1.0FTE required. (4 people) | £60k |  | Control | 2021-04-16
Project Team
Supplier Representatives |  |  | Internal Team |  |  | Customer Representatives
Name | Supplier | Title | Name | Function | Role | Name | Cust. | Title
|  |  | Paul Dombey | Sales
|  |  | Parker Peps | Finance
|  |  | Louisa Bagstock | Process
|  |  | Lucretia Tox | Quality
|  |  | Polly Toodle | Logistics