## Gantt
Gantt Chart - Y Fforwm
Task | Days | Start Date | Finish Date | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85
Enabling Works | 11
Site Set-up | 5 | 2020-05-06 | 2020-05-12
Site Clearance | 4 | 2020-05-13 | 2020-05-18
Investigate for Existing Services | 2 | 2020-05-19 | 2020-05-20
Sub-Structure Works | 24
Piling Works | 9 | 2020-05-21 | 2020-06-02
Install Drainage | 7 | 2020-06-03 | 2020-06-11
Install Shuttering & Formwork | 4 | 2020-06-09 | 2020-06-12
Pour Foundations | 4 | 2020-06-12 | 2020-06-17
Super Structure Works | 45
Structural Steel Works | 15 | 2020-06-18 | 2020-07-08
Install Pre-cast Stair Cases | 3 | 2020-07-06 | 2020-07-08
Install First Floor Slab & Reinforcement | 5 | 2020-07-09 | 2020-07-15
Install Pre-cast Stair Cases (First Floor) | 2 | 2020-07-16 | 2020-07-17
Install Second Floor Floor Slab & Reinforcement | 5 | 2020-07-20 | 2020-07-24
External Brickwork | 15 | 2020-07-09 | 2020-07-29
External Facades | 16
Cladding Systems (Aluminium) | 9 | 2020-07-09 | 2020-07-21
Curtain Wall | 7 | 2020-07-09 | 2020-07-17
Internal Finishes | 46
Elevator Installation | 5 | 2020-07-22 | 2020-07-28
Plumbing Works | 7 | 2020-07-22 | 2020-07-30
Carpentry Works | 8 | 2020-07-22 | 2020-07-31
Electrical Works | 8 | 2020-07-22 | 2020-07-31
Services/Finishes | 7 | 2020-07-31 | 2020-08-10
Drylining | 6 | 2020-08-03 | 2020-08-10
Decorating Works | 5 | 2020-08-10 | 2020-08-14
Final Fixtures and Snagging | 3 | 2020-08-17 | 2020-08-19
Watertight | 9
Roof Structures | 4 | 2020-07-09 | 2020-07-14
Roof Tiling | 5 | 2020-07-15 | 2020-07-21
Post Construction Works | 3
Site Clearance | 3 | 2020-08-20 | 2020-08-24
154

## Labour & Cost
Y Fforwm - Labour & Cost Report
1 day = 8am - 5pm (1 hour break)
Task | Days | Labourer | Quantity | Rate £/hr | Total Cost
Essential Workers Required Full Duration | 79 | Site Manager | 1 | 25.85 | 16337.2
| 79 | Ass. Site Manager | 1 | 15.47 | 9777.04
| 79 | Engineer | 1 | 20.63 | 13038.16
| 79 | Site Foreman | 1 | 15.51 | 9802.32
| 79 | Forklift Driver | 1 | 15.51 | 9802.32
| 45 | Forklift Driver 2 | 1 | 15.51 | 5583.6
Enabling Works | 11
Site Set-up | 5 | Groundworker | 3 | 12.5 | 1500
Site Clearance | 4 | Groundworker | 6 | 12.5 | 2400
Investigate for Existing Services | 2 | Groundworker | 4 | 12.5 | 800
Sub-Structure Works | 24
Piling Works | 9 | Groundworker | 9 | 12.5 | 8100
Install Drainage | 7 | Groundworker | 9 | 12.5 | 6300
Install Shuttering & Formwork | 4 | Groundworker | 9 | 12.5 | 3600
Pour Foundations | 4 | Groundworker | 9 | 12.5 | 3600
Super Structure Works | 45
Structural Steel Works | 15 | Specialist Role | 7 | 31 | 26040
Install Pre-cast Stair Cases | 3 | Specialist Role | 7 | 29.75 | 4998
Install First Floor Slab & Reinforcement | 5 | Specialist Role | 7 | 31 | 8680
Install Pre-cast Stair Cases (First Floor) | 2 | Specialist Role | 7 | 29.75 | 3332
Install Second Floor Floor Slab & Reinforcement | 5 | Specialist Role | 7 | 31 | 8680
External Brickwork | 15 | Bricklayer | 5 | 20 | 12000
External Facades | 16
Cladding Systems (Aluminium) | 9 | Specialist Role | 6 | 35 | 15120
Curtain Wall & Windows | 7 | Window Fitter | 6 | 24 | 8064
Internal Finishes | 46
Elevator Installation | 5 | Specialist Role | 5 | 35 | 7000
Plumbing Works | 7 | Plumber | 8 | 25.5 | 11424
Carpentry Works | 8 | Carpenter | 9 | 22.25 | 12816
Electrical Works | 8 | Electrician | 9 | 25.5 | 14688
Services/Finishes | 7 | Carpenter | 6 | 22.25 | 7476
Drylining | 6 | Dryliner | 7 | 20 | 6720
Decorating Works | 5 | Painter | 8 | 16.25 | 5200
Final Fixtures and Snagging | 3 | Dryliner | 7 | 20 | 3360
| 3 | Carpenter | 3 | 22.25 | 1602
Watertight | 9
Roof Structures | 4 | Carpenter | 9 | 22.25 | 6408
Roof Tiling | 5 | Tiler | 7 | 25.5 | 7140
Post Construction Works | 3
Site Clearance | 3 | Groundworker | 3 | 12.5 | 900
|  | Total Labour Cost |  |  | 262288.64

## Resources
Y Fforwm - Resources Report
Equipment / Machinery | Days | Quantity | Day Rate | Total Cost
Forklift 1 | 79 | 1 | 200 | 15800
Forklift 2 | 68 | 1 | 200 | 13600
Excavator | 31 | 2 | 225 | 13950
JCB | 79 | 2 | 200 | 31600
Crane (Large) | 15 | 1 | 550 | 8250
Crane (Small) | 18 | 2 | 400 | 14400
Piling Rig | 9 | 1 | 875 | 7875
Mortar Silo | 16 | 1 | 250 | 4000
|  | Total Cost |  | 109475
Site Compound | Days |  | Day Rate | Total Cost
Herras Fencing | 79 |  | 125 | 9875
Gate & Pedestrian Gate | 0 | Purchase |  | 4225
Site Office Unit (inc small equipment) | 79 |  | 420 | 33180
Welfare Unit (toilet, Kitchen, etc. inc small equip) | 79 |  | 450 | 35550
Generator | 79 |  | 55 | 4345
Fuel Tank | 79 |  | 40 | 3160
Health & Safety Singage | 0 | Purchase |  | 2500
Storage Unit | 79 |  | 350 | 27650
First Aid Equipment | 0 | Purchase |  | 500
|  | Total Cost |  | 120985