## Slide 1: ACBA 4000 - Session 6
Management Contracting Procurement

## Slide 2: Management Procurement
What are the key challenges and benefits associated with using management contracting procurement in the UK construction industry?
What are the key benefits associated with partnering procurement models, and how do they impact project outcomes and collaboration among the stakeholders
What are the benefits and drawbacks of framework agreements in the construction industry, and how do they impact project delivery and procurement processes?

## Slide 3: 3. Management Procurement 3% (2022 = 1%)
In contrast to the previous two, the client may decide to appoint a Management Contractor to engage and manage several work package SC’s. (still with the use of a form of client consultant/designer)
Competitive due to MC being invited to submit a bid to manage the project, this would include:
  MC Quotation (management and MC preliminaries costs), usually a %age
  The programme
  Procurement of the work packages (competitive)
  Control of information flow
  Buildability considerations

## Slide 4: Some points to note….
Management contractor is appointed early in the project
Costs can be reduced by about 10%
Buildability of design
Time reduced by 20% = possible for some works packages to be tendered early e.g. piling package

## Slide 5: Partnering Agreements 3% (trust, trust & trust)
Partnering (alliancing) was viewed as a radical departure from the traditional Main C approach.
Developed in US in 1980’s and putting relationships as the focus.
Successful partnering relies heavily on teamwork and mutual trust, by openness and honesty by all members of the construction supply chain! (famous pioneering PA = M&S and Bovis)
This has been split into the following informal arrangement:
Mostly it is an informal agreement but can also be made formal by a Partnering contract agreement e.g. NEC Partnering Agreement (or just a charter) PTO

## Slide 6
All parties seek ‘win-win’ solutions (risk management)
Value is placed on long term relationships
Trust & Openness are norms
An environment for long term profitability exists (disclose profit margins & ring fence)
All are encouraged to openly address any problems
All understand that no one benefits from exploitation of the others
Innovation is encouraged (value engineering)
Each partner is aware of the other's needs, concerns and objectives and is interested in helping their partner achieve this (could be via benchmarking the project)

## Slide 7: Partnering going forward
Since 2010 many clients across many sectors have been adopting partnering arrangements with the supply chain as it has proven long-term benefits.
Options of Project Partnering to Strategic Partnering
Latest data on partnering procurement for Clients:
  Up to 40% savings on project costs !
  Up to 70% savings on project time!!
  For contractors the continuity of working repeatedly for the same Client can bring a number of benefits, but contractors agree profit margins increase but also provides a more rewarding environment in which to operate.

## Slide 8: Some points to note….
Good for high-risk contracts – hospitals, schools etc.
Set up a ‘virtual company’
Longer the project the better the partnering results have been found to be – strategic partnering
Latham liked partnering – not based on lowest cost but best value for the client
Risk – is it just a paperwork exercise? Client ties the MC into a thought contract of old!!!

## Slide 9: Framework Agreements 3% (flexibility for Client)
These are being increasingly used to procure goods and services in both public and private sectors. (A form of strategic partnering)
BA were the first big private sector client to use FA’s. LA’s have been using these agreements for a number of years.
The key problem with frameworks is how to compare an ‘economic test’ for the selection process (best value test)
They are usually for a given period of time (max is 4-5 years) and agree a price and standard of quality for a contract.
PQQ for SC to complete to be placed on a selected framework list.

## Slide 10: Framework Agreements
In a nutshell: ‘a flexible procurement agreement between parties, which states that works, services or supplies of a specific nature will be undertaken or provided with agreed T&C (T&C are difficult in law), when selected for a particular need’ usually in an ‘open-book agreement’
However, a FA is simply a promise and not a guarantee of work!
ProCure21+: since the start of the original ProCure21 framework in 2003, over 600 schemes (collectively worth £3.5bn) have been completed, with consistent time and budget compliance of over 90%.

## Slide 11: Some points to note….
‘call off’ basis, for when clients are continually commissioning construction work – not usually a contract
Clients framework should define the scope, locations and construction works that will be requires
Suppliers of goods (e.g. materials), services (e.g. design) and works (e.g. construction) will then provide the client with a pricing mechanism (to include risks) for different types of projects e.g. Schedule of Rates inc. O/H & P & Risk.
Client could then simply select a suitable supplier of goods from the framework to complete the works – no guarantee of this though!
Come in for a bit of criticism lately….

## Slide 12: Your Thoughts….
Trust is generally regarded as being key to the success of partnering! How could this culture be best achieved by all parties of the project?
What are your 5 or 6 advantages to framework agreements?