## Slide 1: Managing Projects in the Organisation
“Health and safety training projects in order to motivate the Workers for Smith Brothers Ltd.”
Student name: Kamrul Hasan
Student ID: 2023331
Module name: Managing projects in the organisation
Module Code: BMSW 5104
Lecturer name: Terry Walcott
Level 5
Term 1 Group 1

## Slide 2: Introduction and Objectives
Smith brothers Limited is a London based business that offers the best selection of pre-owned Scania trucks in the UK. They have a wide range of body types that can satisfy different groups of customers. It is a family run business that was established in 1969 and consistent in providing first class service to the customers.
The first objective of the project is to provide Primary health and safety training and behavior to the current employees
The second objective is to identify the key risks that are often considered as minor incidence.

## Slide 3: The main reasons for selecting the project
Employees are often fall from the ladders
Employees are responsible for the coloring of the trucks
Employees are responsible to fix the trucks
Employees a responsible to lifting the trucks with machinery

## Slide 4: Activators, Behaviors, Consequences (ABC) CHART
Activators
Employee is do not take the necessary precaution while working under the trucks
Employees do not use mask when dealing with colors
Behaviors
Employees are overconfident about their protection while working under the trucks
Employees are reckless about wearing necessary protective equipment while dealing with colors
Consequences
It can cause great harm to their health and in the worst case cause them their lives.
It can damage their eyes and smelling ability at the primary level

## Slide 5: Scope of the Project
Right now everyone is conscious about their health regardless of their working environment but in the case of small and medium size businesses most of them do not want to engage in safety and healthcare issues because of the lack of knowledge.
The project will target all of the employees of the organisation and develop their knowledge about the importance of ensuring their own safety along with others and how to maintain a safe work environment
As the business is dealing with heavy equipment it is a necessary project as there can be any accident anytime and everyone should be prepared for this kind of incident.

## Slide 6: Stakeholder Analysis
The primary stakeholders would be the owners of the business along with the executives who are responsible for the management of the business. They will get high priority.
The second category of stakeholders should be the employees who are responsible to deal with the trucks and other equipment and maintenance of the trucks. This group of stakeholders will also get high priority.
The third category of the stakeholders are the customers and financial supporters who are closely connected with the business and often deal with the business.
In order to manage the stakeholders the project will first provide a brief explanation about the necessity of the project and clarify what the project wants to achieve.

## Slide 7: Importance of the Project
The primary purpose of the training is to develop awareness among the employees and other stakeholders so that everyone has the necessary idea about safety and health training.
This project will also help the stakeholders especially the employees to develop a positive attitude towards health safety
This project will also help the employers to understand the legal duties associated with the safety of the employees in the working environment
This project will help to understand the financial cost of accidents that the organization may need to take care of.

## Slide 8: The Iron Triangle
Time - the project should be a four day long project that involves every employees of the organization, therefore it is viable for the organization to complete the project on time
Cost - the budget of the project will not be high like any other project because only some of the professional trainers will provide the necessary training to the employees
Quality Performance - with the help of the project it is expected that the employees will understand the necessity of safety in the working environment and how to help each other in case of any incident.

## Slide 9: Success Factors
This particular project aims to make the employees compliant with workplace safety and behavior. Professional trainers will provide the necessary guidelines, training and Advisors to make the employees confident about their safety in the work environment.
After the successful completion of the project it is expected that the employees will be more focused about their own safety concerns and work carefully with heavy equipment.

## Slide 10: Gantt Chart
 | Day 1 | Day 2 | Day 3 | Day 4
Basic information about safety |  |  |  | 
Healthcare safety |  |  |  | 
Workplace safety |  |  |  | 
Legal understandings |  |  |  | 

## Slide 11: References
Kendall I.G., Rollins C.S. (2003). Advanced Project Portfolio Management and the PMO, J. Ross Publishing, Inc.
Kušar J., Rihar L., Kisiček K., Starbek M. (2004). Experiences at Project Management Office Implementation. Project network of Slovenia, vol. 7, no. 4, p. 42-46
Meredith R.J., Mantel J.S. (2003). Project Management, A Managerial Approach (fifth edition), John Wiley &vSons, Inc.
PMBOK Guide (2004). A guide to the project management body of knowledge, 3rd ed., Newtown Square: Project Management Institute.