## Sheet1
GANTT CHART - INITIAL
PROJECT TITLE |  | Rod & Bar Mill - Project |  |  |  |  | COMPANY NAME | [5 empty] | Celsa Manufacturing UK Ltd
PROJECT MANAGER |  | Garin Thomas Mann |  |  |  |  | DATE | [5 empty] | 8th October 2020
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION (WEEKS) | % OF TASK COMPLETE | PHASE ONE - 08/10/2020-19/11/2020 | [5 empty] | PHASE TWO - 19/11/2020-31/12/2020 | [5 empty] | PHASE THREE - 31/12/2021-11/03/2021 | [9 empty] | PHASE FOUR - 11/03/2021-13/05-2021
[6 empty] | 2020-10-08 | 2020-10-15 | 2020-10-22 | 2020-10-29 | 2020-11-05 | 2020-11-12 | 2020-11-19 | 2020-11-26 | 2020-12-03 | 2020-12-10 | 2020-12-17 | 2020-12-24 | 2020-12-31 | 2021-01-07 | 2021-01-14 | 2021-01-21 | 2021-01-28 | 2021-02-04 | 2021-02-11 | 2021-02-18 | 2021-02-25 | 2021-03-04 | 2021-03-11 | 2021-03-18 | 2021-03-25 | 2021-04-01 | 2021-04-08 | 2021-04-15 | 2021-04-22 | 2021-04-29 | 2021-05-06 | 2021-05-13
1 | SELECT & SPECIFY- Project Conception and Initiation
1.1 | Initial Gantt Chart (First Draft) | 2020-10-08 | 2020-10-15 | 1 | 0% | 2021-04-29: FINISH
1.2 | Produce a weekly logbook template (To be filled out each week) | 2020-10-08 | 2020-10-15 | 1 | 0% | bar: 2020-10-08
1.3 | Research current maintenance problems within work | 2020-10-15 | 2020-10-22 | 1 | 0% | bar: 2020-10-15
1.4 | Brainstorm the maintenance problems, producing solutions | 2020-10-15 | 2020-10-22 | 1 | 0% | bar: 2020-10-15
1.5 | Select three of the brainstormed projects to use | 2020-10-15 | 2020-10-22 | 1 | 0% | bar: 2020-10-15
1.6 | Research further evidence on the three potential projects | 2020-10-22 | 2020-10-29 | 1 | 0% | bar: 2020-10-22
1.7 | Create project charters for each of the three potential projects | 2020-10-22 | 2020-10-29 | 1 | 0% | bar: 2020-10-22
1.8 | Evaluate the three potential projects and choose a project to use | 2020-10-29 | 2020-11-05 | 1 | 0% | bar: 2020-10-29
1.9 | Create product design specifcation for the selected project | 2020-11-05 | 2020-11-12 | 1 | 0% | bar: 2020-11-05
1.1 | Develop three potential solutions for the chosen project | 2020-11-05 | 2020-11-12 | 1 | 0% | bar: 2020-11-05
1.11 | Evaluate three potential solutions against my PDS & 2 other methods | 2020-11-12 | 2020-11-19 | 1 | 0% | bar: 2020-11-12
1.12 | Select the best solutions based on results | 2020-11-12 | 2020-11-19 | 1 | 0% | bar: 2020-11-12
2 | PLAN & MONITOR - Project Definition and Planning
2.1 | Develop a project plan | 2020-11-19 | 2020-11-26 | 1 | 0% | bar: 2020-11-19
2.2 | Revisit initial Gantt Chart and improve if necessary | 2020-11-26 | 2020-12-03 | 1 | 0% | bar: 2020-11-26
2.3 | Finalise initial sketches | 2020-12-03 | 2020-12-10 | 1 | 0% | bar: 2020-12-03
2.4 | Produce 3D modelling and CAD drawings | 2020-12-10 | 2020-12-17 | 1 | 0% | bar: 2020-12-10
2.5 | Produce a Design Brief | 2020-12-17 | 2020-12-24 | 1 | 0% | bar: 2020-12-17
2.6 | Produce a Product Design Specification (PDS) | 2020-11-24 | 2020-12-31 | 1 | 0% | bar: 2020-12-24
3 | IMPLEMENT- Project Conception and Initiation
3.1 | Produce a Product Legislation | 2020-12-31 | 2021-01-14 | 2 | 0% | bar: 2020-12-31 to 2021-01-07
3.2 | Produce a Product Ethics | 2021-01-14 | 2021-01-28 | 2 | 0% | bar: 2021-01-14 to 2021-01-21
3.3 | Produce Project Activities & Progression | 2021-01-28 | 2021-02-11 | 2 | 0% | bar: 2021-01-28 to 2021-02-04
3.4 | Produce a Critical Path Analysis | 2021-02-11 | 2021-02-25 | 2 | 0% | bar: 2021-02-11 to 2021-02-18
3.5 | Implement the Product | 2021-02-18 | 2021-02-25 | 1 | 0% | bar: 2021-02-18
3.6 | Create a Standard Operating Procedure | 2021-02-25 | 2021-03-11 | 2 | 0% | bar: 2021-02-25 to 2021-03-04
4 | PRESENT- Project Performance / Monitoring
4.1 | Continuosly monitor the performance of the project | 2021-03-11 | 2021-04-29 | 7 | 0% | bar: 2021-03-11 to 2021-04-22
4.2 | Prepare Final Project Report (Working Document) | 2021-03-11 | 2021-04-29 | 7 | 0% | bar: 2021-03-11 to 2021-04-22
4.3 | Prepare Final Powerpoint Presentation | 2021-03-11 | 2021-04-29 | 7 | 0% | bar: 2021-03-11 to 2021-04-22
4.4 | Complete a weekly review into my Logbook | 2020-10-08 | 2021-04-29 | 29 | 0%