| Local Authority | Swansea |
| --- | --- |
| Year | 2026 |
| Student Name |  |
| Project Focus | street games |
| Time of year | Summer- APRIL - JULY |
| Funding from street games | £2000 |

# Background Research – Include research here into the area of Swansea and information that has helped you reach a decision on activities to be planned and developed.

# Across Wales, roughly 39% of children and adults participate in sport 3+ times per week, with girls / women reporting lower participation than boys / men (36% vs 43%) — showing a persistent gender gap in sporting engagement. Children in socio-economically deprived areas have lower participation (32%), indicating a need for accessible, community-based programmes. (Sport Wales, 2024)

# Summer holiday programmes in Swansea have attracted over 1,400 children across 150+ sessions, showing strong community interest. (Swansea City Council, 2023)

- PLANNED ACTIVITIES

| Identified Activity / Project INCLuDING NAME / LOCATION / DAY /TIME | How will the project be developed? what will it look like? how will it be promoted? who will deliver it? | WHO ARE THE PARTNERS THAT WILL HELP DEVELOP THE SESSION? WHAT WILL BE THEIR INVOLVEMENT? | WHAT WILL SUCCESS LOOK LIKE. start / middle / end of plan |
| --- | --- | --- | --- |
| Door step sport Football Location: Swansea university sports centre Day/Time: Fridays, 6:00pm – 7:30pm | Weekly informal 5v5 football sessions. Open access – no booking required. Music playing to create atmosphere. Small-sided games, skill challenges, mini-tournaments. Young people help referee and organise teams (leadership opportunities). Cones set up for 2 small pitches. Portable goals. High-energy, inclusive, relaxed environment. Hoodies, bibs, floodlights (if available). Positive youth-worker presence. How will it be promoted? Flyers through local schools. Social media posts in community groups. Word of mouth via youth workers. Posters in local shops & community centre. Who will deliver it? Level 1/2 qualified football coach. Youth support worker. Volunteer young leaders (14–18 yrs). | Swansea university sports centre Local FA Development Officer – equipment support & coach mentoring. Secondary School PE Department – promote to students. | Start: 8–10 young people attending regularly. Positive engagement and safe environment established. Middle: 15–20 consistent participants. Reduction in anti-social behaviour locally on Friday evenings. 2 young people progressing into leadership roles. End: Sustainable weekly session. Young leaders helping run sessions. Pathways created into local football clubs or referee courses. |
| Door step sport Multi-Sport Fitness Location: Ashleigh Road Playing Fields/LC2 Day/Time: Wednesdays, 4:30pm – 6:00pm | How will the activity project be developed? Rotating activities: football shoot-outs, dodgeball, circuit training, street cricket. 20-minute activity blocks to maintain engagement. Music and small rewards (water bottles, certificates). Focus on fun, fitness, and teamwork. What will it look like? Pop-up stations with cones and equipment for activity. Fitness circuit area with resistance bands and bodyweight stations. Bright branded banners to make it visible and welcoming. How will it be promoted? School assemblies & lunchtime demos. TikTok/Instagram short clips (with consent). Local youth club referrals. Parent WhatsApp groups. Who will deliver it? Multi-sport qualified coach. Female sports activator (to encourage girls’ participation). Community volunteers. | Youth Service – referral of young people at risk of disengagement. Local sports clubs – provide pathways to consistent fitness in specific sports. LC2 – storage and facility use | Start: 10–12 young people attending first week. Equal mix of boys and girls encouraged. Middle: Increased confidence and fitness levels. 20+ regular participants. At least 3 participants joined to external sports clubs. End: Recognised as a safe weekly hub. Measurable improvements in attendance, behaviour, or wellbeing (feedback forms). |
| US Girls Dance & Empowerment Project Location: Volcano Theatre Day/Time: Tuesdays, 5:00pm–6:30pm Target Group: Girls aged 11–16 | How Will the Project Be Developed? The project will run as a 12-week structured programme focusing on: Street dance and contemporary movement Confidence-building workshops Body positivity and self-esteem sessions Creative choreography development Leadership opportunities for older participants Sessions will gradually move from basic movement skills to group choreography and performance preparation. Consultation with local schools and youth workers will take place before launch to understand barriers to participation (confidence, cost, transport, cultural considerations). What Will It Look Like? Each session will follow a clear structure: Start (Weeks 1–4): Foundation Phase Icebreakers and trust-building activities Basic dance technique Confidence and identity workshops Guest female role model speaker Middle (Weeks 5–9): Development Phase Choreography creation in small groups Peer mentoring (older girls supporting younger girls) Filming rehearsals for reflection Mid-programme sharing session for parents End (Weeks 10–12): Showcase Phase Final rehearsals Performance event at Volcano Theatre Certificates and celebration event Feedback and progression signposting The environment will feel safe, supportive, female-led, and empowering. How Will It Be Promoted? Posters in local secondary schools Social media promotion via community pages Partnership referrals from youth services Promotion through Swansea Council youth networks Word-of-mouth ambassadors from participants Who Will Deliver It? Qualified female dance instructor Youth worker (safeguarding trained) Guest teachers (female entrepreneurs, performers, university students) | Swansea Youth Service – Participant referrals & safeguarding support Women Connect First – Confidence and empowerment workshop support Local secondary schools – Promotion and venue links if needed | What Will Success Look Like? 15–20 girls attending consistently Increased confidence reported in exit surveys At least 70% completing the full 12 weeks Participants progressing into leadership or further arts programmes Positive parental feedback A final showcase event well attended by family and friends |
| Club One Athletics Program Location: Swansea Athletic Track Day / Time: Saturdays, 9:00 AM – 12:00 PM 3 month program | How will the project be developed? Phase 1 – Planning: Identify target age groups (12–18), recruit coaches, set up equipment (cones, hurdles, timing systems). Phase 2 – Implementation: Conduct weekly training sessions focusing on sprinting technique, endurance, and speed drills. Include a mini-tournament every 4 weeks to track progress. Phase 3 – Evaluation: Collect participant feedback, performance data, and attendance to assess improvement and engagement. What will it look like? Outdoor track sessions with structured warm-ups, sprint drills, relay exercises, and strength-building activities. Sessions divided into skill-based groups: beginners, intermediate, and advanced athletes. Use of visual aids and demonstration videos for technique correction. How will it be promoted? Social media campaigns (Instagram, TikTok) showcasing highlights and tips from sessions. Flyers at local schools, community centers, and sports clubs. Partnerships with local sports organizations and youth clubs to spread awareness. Who will deliver it? Lead Coach: Certified athletics coach specializing in sprints. Assistant Coaches: Volunteer athletes or college-level runners to provide one-on-one guidance. Guest Trainers: Occasionally invite elite athletes for masterclass sessions. | Local Schools: Promote participation, provide initial recruitment, allow access to students. Swansea athletics Club: Provide volunteers and equipment support. Health & Fitness Brands: Sponsor hydration, nutrition guidance, and minor incentives like T-shirts or medals. | Increased participant skill levels measured through timed sprint improvements. High retention and attendance rates over the 12-week program. Positive feedback from participants and parents. A community mini-tournament showcasing improved skills at the end of the program. Start / Middle / End of Plan Start (Weeks 1–2): Recruitment, equipment setup, initial fitness assessments, orientation session. Middle (Weeks 3–10): Weekly training sessions, ongoing skill evaluation, mid-program mini-tournament, feedback collection. End (Weeks 11–12): Final assessments, awards and recognition, showcase mini-tournament, collection of feedback for next season. |

Costings

| Activity / project / session | Resources Needed | Estimated spend | Estimated Income Generated For / by the activity / session |
| --- | --- | --- | --- |
| Example Skate and Scoot Session | Coach to provide instruction 1000 Promotional postcards | 12 sessions @ £10 = £120 £365 Total spend- £485 | £1 per session £240 income Total income- £240 |
| football | Purchase of 2 portable 5v5 football goals Football equipment (15 balls, cones, bibs, pump, first aid kit) Qualified football coach delivery (1.5 hrs x 10 weeks) Youth support worker supervision (10 weeks) Facility hire (floodlit pitch, 10 weeks) Healthy refreshments (water & fruit, 10 weeks) Printing of flyers and promotional posters | –£400 – £200 – £600 – £400 – £200 – £150 – £50 Total Estimated Spend – £2,200 | £3 x 15 participants x 10 weeks = £450 Small Be Active Wales Fund = £500 Small FAW grant = £250 Total Estimated Spend - £2,200 |
| Multi-Sport Fitness | Portable goals and multi-sport starter equipment Dodgeballs, cricket sets, resistance bands, agility ladders and cones Qualified multi-sport coach delivery (10 weeks) Female support staff (10 weeks) Participation incentives (water bottles, certificates, small rewards) Marketing and social media promotion materials Public liability insurance and space permits | – £500 – £300 – £700 – £400 – £200 – £50 -£150 Total Estimated Spend – £2,300 | Participant subs (£1.50 per participant, average 20 participants, 10 weeks) – £300 Public Health Wales small grant funding – £1,200 Be Active Wales Fund – £800 Total Estimated Income – £2,300 |
| Dance & Empowerment Project | Venue hire – Volcano Theatre (12 sessions) Qualified female dance instructor (12 sessions) Youth worker (safeguarding trained, 12 sessions) Workshop materials (mats, props, music licensing, stationery) Marketing and social media promotion Filming / editing equipment– £100 Certificates & awards for participants Refreshments (light snacks & drinks Transport support (if required for participants) | – £600 – £480 – £300 – £120 – £80 – £100 –£50 – £60 – £100 Total Estimated Spend – £2,040 | Participant fees (£1 per participant, average 15 girls, 12 weeks) – £180 Local youth service grant – £1,200 Community arts funding – £660 Total Estimated Income – £2,040 |
| athletics | Track rental and space permits Qualified athletics coach delivery (12 weeks) Assistant coaches / volunteer support (12 weeks) Participation incentives (medals, certificates, water bottles) Marketing and social media promotion materials Public liability insurance | – £400 – £900 – £300 – £250 – £50 – £100 Total Estimated Spend – £2,350 | Be Active Wales Fund - £2,350 Total Estimated Income – £2,350 |
|  |  | Total Cost of plan- = £8,890 | Estimated funds available- = 8,890 |

1000 Word Written piece: Students are required to carry out a research task and highlight the current barriers to sports participation in deprived communities. Students should consider what the internal and external issues are affecting sports development organisations when planning to deliver sports development projects in deprived communities.

Sports participation is widely recognised as a key contributor to physical health, mental well-being, and social cohesion. However, not all communities have equal access to sporting opportunities, with people living poorer areas often facing more barriers that prevent regular engagement in physical activity. These barriers can be more than just financial, they may also be logistical, social, or cultural, these issues will stack up on top of each other causing people in some areas to not be able to access sports teams or fitness areas (gyms, leisure centres and other public or privately owned places to exercise). This essay will examine the current barrier to sports participation in deprived communities exploring both internal issues within sports organisations, such as limited resources and staff capacity, and external factors including social economic disadvantage, accessibility constraints, and cultural perceptions. By looking at these factors this essay aims to provide an understanding of the challenges in promoting sports participation and highlight potential strategies for effective sports development in poorer and less developed areas.

One of the most significant barriers to sports participation for most people living in deprived communities is financial constraint and socioeconomic disadvantage. Both individuals and families living in low-income areas often struggled to afford the direct costs associated with engagement in organised sport, such as gym memberships, equipment purchases, on the expense of transport to venues (Steenhuis et al., 2009). These financial barriers Are made worse by cost-of-living pressures, meaning that sport is not apriority when households must allocate limited funds 2 essentials such as food, housing, and other bills (Sport Scotland, 2024). Research shows that socioeconomic status correlates with participation levels, with lower engagement found among individuals from disadvantaged backgrounds due to both monetary and opportunity costs that come along with sport (Elhakeem et al., 2015). When people perceive sport as a luxury rather than an accessible activity, participation rates in lower economically sound areas remain lower than in more wealthy areas.

A second significant barrier into sports participation for people living in deprived areas is access to sports facilities and programmes, these can be significantly limited by logistical challenges. Many of these communities experience a shortage of safe, nearby sports venues, which requires residents to travel further distances often without adequate transport options (Garner-Purkis et al., 2020). In addition, awareness of available programmes is frequently low, with residents unaware of affordable community-based opportunities (Garner-Purkis et al., 2020). These accessibility-based issues mainly affect children, adolescence, and women Who may have additional restrictions on mobility due to childcare responsibilities, safety concerns, or cultural expectations (Sport England, 2024). Without addressing these logistical barriers, even well-funded programmes may struggle to achieve meaningful engagement, as the physical and informational gaps in access limit community engagement.

Thirdly, social and cultural factors strongly influence participation in sports in deprived communities. Psychological barriers such as fear of judgement, low self-confidence, or perceptions of inability, can prevent individuals from joining organised sports (Ljungmann et al., 2022). Gender norms and cultural expectations also shape who participates; for example, adolescent girls in deprived areas are less likely to engage due to societal pressures and a lack of female role models in sports (StreetGames, 2015). Pay influence also affects engagement, as people’s participation often correlate with their friend groups and social circles. So, it is critical sports organisations make their programmes fit the local community and are welcome to everyone so more people will take part.

Sporting organisations in more deprived areas also face internal and external challenges that affect their ability to deliver relevant and effective programmes to the communities they serve. Internally, organisations often struggle with limited funding, insufficient staff training and operational capacity constraints, which Affects their ability to provide consistent and inclusive sport programmes (Sport England, 2024). Externally, organisations often struggle to navigate policies that prioritise short term funding over sustainable long-term investment, whilst also contending with structural in a qualities such as inadequate transport infrastructure or poorly maintained facilities (Steenhuis et al., 2009). Additionally, building trust and engagement within communities requires a lot of time, manpower, and culturally sensitive approaches, which many organisations underestimate. These internal and external factors worsen the barriers faced by many people who want to participate in organised sport, demonstrating that effective sports development in deprived areas requires addressing both community and organisational challenges at the same time.

To conclude, sports participation in communities with lower economic backgrounds is hindered by multiple different factors such as financial, logistical, social, and cultural barriers, which or made worse by the internal and external challenges faced by sporting organisations. Financial constraints, lack of access, social norms, and psychological barriers or reduce engagement, while organisations must limit resources, how many people they can reach, And policy pressures. Addressing these significant barriers and other barriers requires an approach that will combine a community centre design, affordable programming, accessible and adequate facilities.

Reference list

Elhakeem, A., Cooper, R., Bann, D. and Hardy, R. (2015). Childhood socioeconomic position and adult leisure-time physical activity: a systematic review. International Journal of Behavioral Nutrition and Physical Activity, 12(1). doi:https://doi.org/10.1186/s12966-015-0250-0.

Garner-Purkis, A., Alageel, S., Burgess, C. and Gulliford, M. (2020). A community-based, sport-led Programme to Increase Physical Activity in an Area of deprivation: a Qualitative Case Study. BMC Public Health, [online] 20(1). Available at: https://bmcpublichealth.biomedcentral.com/articles/10.1186/s12889-020-08661-1.

Ljungmann, C.K., Christensen, J.H., Klinker, C.D., Pawlowski, C.S. and Johnsen, H.R. (2022). P03-14 Barriers to sports participation among adolescent girls from deprived neighbourhoods. European Journal of Public Health, 32(Supplement_2). doi:https://doi.org/10.1093/eurpub/ckac095.050.

Sport England. (2024). Research: What Motivates One Group to Be Active Might Be a Barrier to another. That’s Why We Conduct Research into How Different People Get Active and What Prevents Them from Doing so. [online] Available at: https://www.sportengland.org/research-and-data/research.

Sport Wales. (2024). Available at: https://www.sport.wales/files/f28cd99e0e2a02dce860d6e9f1e59268.pdf? [Accessed 23 Feb. 2026].

Sportscotland (2024). Equality and Sport Research 2024. [online] Sportscotland the National Agency for Sport in Scotland. Available at: https://sportscotland.org.uk/about-us/equality-diversity-and-inclusion/equality-and-sport-research/equality-and-sport-research-2024/learning-notes/poverty-and-low-income?.

Steenhuis, I.H.M., Nooy, S.B.C., Moes, M.J.G. and Schuit, A.J. (2009). Financial Barriers and Pricing Strategies Related to Participation in Sports Activities: The Perceptions of People of Low Income. Journal of Physical Activity and Health, [online] 6(6), pp.716–721. doi:https://doi.org/10.1123/jpah.6.6.716.

StreetGames. (2015). StreetGames Report: Delivering sport to young people in deprived areas. https://www.sportanddev.org/sites/default/files/downloads/streetgames_report_3_12_15_final_with_cover.pdf

Swansea City Council (2023). Annual view of performance 2021/22. https://www.swansea.gov.uk/media/11704/Annual-review-of-performance-2021---2022/pdf/Annual_Review_of_Performance_2021-22_ENG.pdf?