## Semester 1
BMPS6012 and BMPL6008 Independent Project
Name
Start Date | 2023-09-25
Submission | 2024-05-07
Total days | 225
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33
Tasks | Week beginning | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29 | 2024-05-06
1 | Induction & Initial Thoughts | 2023-09-25: 28th Sept
2 | 2-hour Workshop: proposal and ethics form | bar: 2023-10-02
3 | Group Supervision: proposal and ethics form | bar: 2023-10-09
4 | Submit: proposal and ethics form with individual feedback | bar: 2023-10-16
5 | 2-hour Workshop: introduction | bar: 2023-10-23
6 | Group Supervision: introduction | bar: 2023-10-30
7 | Submit: introduction with individual feedback | bar: 2023-11-06
8 | INDUSTRY WEEK | bar: 2023-11-13
9 | 2-hour Workshop: literature review | bar: 2023-11-20
10 | Group Supervision: literature review | bar: 2023-11-27
11 | Submit: literature review with individual feedback | bar: 2023-12-04
12 | 2-hour Workshop: methodology | bar: 2023-12-11
13 | CHRISTMAS BREAK - 18th December - 5th January | bar: 2023-12-18 to 2024-01-01
AFTER CHRISTMAS
14 | Research | bar: 2024-01-08 to 2024-01-22
15 | Group Supervision: methodology | bar: 2024-01-29
16 | Submit: methodology | bar: 2024-02-05
17 | Group Supervision: | bar: 2024-02-12
18 | 2-hour Workshop: analysis | bar: 2024-02-19
19 | Group Supervision: analysis | bar: 2024-02-26
20 | 2-hour Workshop: conclusion and recommendations | bar: 2024-03-04
21 | INDUSTRY WEEK | bar: 2024-03-11
22 | Submit: analysis with individual feedback | bar: 2024-03-18
23 | EASTER BREAK - 25th March - 12th April | bar: 2024-03-25 to 2024-04-08
24 | Submit: conclusion with individual feedback | bar: 2024-04-15
25 | Individual supervision | bar: 2024-04-22 to 2024-04-29
26 | Individual supervision | bar: 2024-04-22 to 2024-04-29
27 | FINAL SUBMISSION DEADLINE

## Semester 2
BMPS6012 and BMPL6008 Independent Project
Name
Start Date | 2021-09-27 | [19 empty] | From Week 22 we have 11 weeks or 75 days remaining to the deadline day of 6th May.
Submission | 2022-05-05
Total days | 220
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Xmas break | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Easter Break | Week 31 | Week 32
Tasks | Week beginning | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 |  | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 |  | 2022-04-25 | 2022-05-02
1 | Face-to-face induction 24.9.21 & initial thoughts
2 | Work through resources on Moodle
3 | Weekly pre-recorded lecture released on Thursdays at 4pm
4 | Online class with Mike
5 | Choose output & topic
6 | Class with Mike: outputs and topics
7 | Online class with Mike: the research proposal; dissertation examples
8 | Supervisor allocated
9 | Diving into your research proposal (Eating Elelephants - 1 & 1a. Guides on Moodle)
10 | 1. Group supervision session: writing the Research Proposal
11 | 1. Individual Supervision: initial discussion topic and proposal. First literature review check
12 | Research proposal submission and feedback
13 | Individual research: building the reference list
14 | Online class with Mike: research philosophies & approaches
15 | Online class with Mike: research methods & ethical considerations
16 | Research design & delivery | bar: 2022-01-03 to 2022-01-24
17 | 2. Group supervision session
18
19 | S1 RAG Review: which students are we worried about? | bar: 2022-01-03
20 | 2. Individual Supervision: progress check. Literature review | bar: 2022-01-10 to 2022-02-14
21 | Research findings | bar: 2022-02-07 to 2022-02-14; 2022-02-28 to 2022-03-21
22 | 3. Group supervision session | bar: 2022-01-24 to 2022-02-21
23 | 3. Individual Supervision: methodology lit review, and research progress | bar: 2022-02-21 to 2022-03-21
24 | Writing up | bar: 2022-02-21 to 2022-03-28
25 | 4. Group supervision session; writing workshop | bar: 2022-02-21 to 2022-03-07
26 | 5. Group supervision session: writing workshop | bar: 2022-03-14 to 2022-03-28
27 | 4. Individual Supervision: introductions & conclusions | bar: 2022-03-28
28 | 6. Group supervision session: inserting declarations & proof-reading | bar: 2022-03-28
29 | Final submission
Formulas:
Week 2 = [Week 1]+7
Week 3 = [Week 2]+7